## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar - II | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Sinking of 250 mm X 150 mm dia 180mt. deep Tube well Drilling by Direct Rotary method and Construction of 5.90 m X 4.10 m Pump room/Chlorine room with sanitary arrangements, 350 CuM OHR with Soil Investigation, laying of Rising main, Distribution System and Providing functional household tap connection, with different works related to Chhota Turigram & its adjoining mouzas water supply scheme within Mayureswar-II Block including supply of all labour & materials under BIRBHUM Division ,PHE Dte. | AE | JE3 | ORD/000082/2024-2025 | 1783/BHM | 14/06/2024 | 14/06/2025 | UNIQUE AGENCY | 533.48 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar - II | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHOTA TURIGRAM ) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000836/2022-2023 | 292/RSD | 02/09/2022 | 17/10/2022 | ENVIROTECH SOLUTIONS | 3.36 | 2.46 | 73.34 | 100
3 | BIRBHUM | Mayureswar - II | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHOTA TURIGRAM) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000837/2022-2023 | 380/RSD | 26/09/2022 | 10/11/2022 | ENVIROTECH SOLUTIONS | 3.29 | 2.85 | 86.53 | 100
4 | BIRBHUM | Mayureswar - II | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 2382/BHM | 27/08/2024 |  | Resource Division | 14.74 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar - II | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1448/BHM | 25/04/2023 |  | Resource Division | 72.7 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar - II | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Supply, Delivery and storage of different Electro-Mechanical Accessories at Chhoto Tuligram PWSS under Bolpur Mechanical Division, PHE,Dte. | Assistant Engineer-III | Junior Engineer | ORD/000513/2024-2025 | 3760/Bol.MD | 12/09/2024 | 12/10/2024 | HINDOL ROY | 40.82 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar - II | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Providing Electro-mechanical accessories and others for Chhoto Turigram PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000843/2023-2024 | 3282/BOL.MD | 29/09/2023 | 28/11/2023 | SINHA ELECTRICALS | 67.61 | 19.53 | 28.89 | 40
8 | BIRBHUM | Mayureswar - II | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Well and other allied works at Chototurigram PWSS under Bolpur Mechanical Division., Block - Mayureswar - II. | Assistant Engineer-III | Junior Engineer | ORD/001190/2023-2024 | 375/Bol.MD | 06/03/2024 | 20/04/2024 | STANDARD ELECTRICALS | 7.41 | 3.67 | 49.5 | 100
9 | BIRBHUM | Mayureswar - II | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION | SM/18513 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Well and other allied works at Chototurigram PWSS under Bolpur Mechanical Division., Block - Mayureswar - II. | Assistant Engineer-III | Junior Engineer | ORD/001193/2023-2024 | 377/Bol.MD | 06/03/2024 | 20/04/2024 | CINZANO | 7.75 | 0 | 0 | 0
Total | [13 empty] | 751.16 | 28.51 | 3.8