## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar - I | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | New | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000385/2023-2024 | 4142/BHM | 19/10/2023 | 15/07/2024 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 0 | 30
2 | BIRBHUM | Mayureswar - I | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | New | Continuation Work Order for Preparation & Submission of DPR for (DAKSHIN GRAM) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | AE | JE3 | ORD/000804/2022-2023 | 291/RSD | 02/09/2022 | 01/12/2022 | ENVIROTECH SOLUTIONS | 3.43 | 2.61 | 75.96 | 100
3 | BIRBHUM | Mayureswar - I | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | New | Continuation Work Order for Preparation & Submission of DPR for (DAKSHIN GRAM) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | AE | JE3 | ORD/000805/2022-2023 | 376/RSD | 23/09/2022 | 22/12/2022 | ENVIROTECH SOLUTIONS | 2.86 | 2.81 | 98.08 | 100
4 | BIRBHUM | Mayureswar - I | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 1461/BHM | 25/04/2023 |  | Resource Division | 84.55 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar - I | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | New | Material Requisition To Resource Division |  |  | RTOR000204/2023-2024 | 205/BHM | 22/01/2024 |  | Resource Division | 7.15 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | New | Quotation For new connection at Dakshingram PWSS P/H -3 (Block- Mayureswar-I) |  |  | BILL/00078/2024-2025 | BP-2024-2025-25 | 20/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.32 | 0 | 0 | null
7 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | New | Quotation for new connection at Dakshingram PWSS P/H-2 (Block-Mayureswar -I) |  |  | BILL/00081/2024-2025 | BP-2024-2025-26 | 20/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.53 | 0 | 0 | null
8 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | New | WBSEDCL QUOTATION FOR DAKSHINGRAM PUMP HOUSE NO-I |  |  | BILL/02079/2023-2024 | BP-2023-24-287 | 04/03/2024 |  | WBSEDCL | 6.44 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | New | Providing Electro-mechanical accessories and others for Dakshingram PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000731/2023-2024 | 3476/Bol.MD | 07/11/2023 | 06/01/2024 | S.P. CONSTRUCTION | 55.2 | 13.51 | 24.47 | 40
10 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division | SM/18521 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Dakhingram PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001217/2023-2024 | 402/Bol.MD | 07/03/2024 | 21/04/2024 | EASTERN INDIA SALES & SERVICE | 24.53 | 0 | 0 | 0
Total | [13 empty] | 2200.84 | 18.92 | 0.86