## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat - I | Birbhum Division | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 1589/BHM | 26/04/2023 |  | Resource Division | 13.11 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat - I | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Providing Electro-mechanical accessories and others for Kashtagara Zone - II PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000914/2023-2024 | 3523/Bol.MD | 29/11/2023 | 28/01/2024 | M/S. DILIP MITRA | 27.61 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat - I | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Providing Electro-mechanical accessories and others for Kashtagara Zone - I PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000916/2023-2024 | 3524/Bol.MD | 29/11/2023 | 28/01/2024 | WEST BENGAL ENGINEERING CO. | 27.68 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat - I | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. | SM/18733 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Kastagara PWSS under Rampurhat - I Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001247/2023-2024 | 524/BOL.MD | 14/03/2024 | 13/05/2024 | S.G.TECHNICAL SERVICES | 7.61 | 0 | 0 | 0
Total | [13 empty] | 76 | 0 | 0