## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 |  |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bahirghanya Piped Water Supply Scheme at Galsi-II Block |  |  | Laying parallel pipeline to increase the water supply towards Kalyanpur [ Node No-146 t0 100 ] of BAHIRGHANNYA and its adjoining mouza's Piped W/S Scheme at Galsi-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000130/2022-2023 | 343/DSD | 30/06/2022 | 30/07/2022 | SUPRIYA RAY | 4.89 | 0 | 0 | 1
2 |  |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bahirghanya Piped Water Supply Scheme at Galsi-II Block |  |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bahirgannya piped water supply scheme at Bahirgannya (04 Nos. habitation Part), Askaran (02 Nos. habitation), Brindabanpur (02 Nos. Habitation), Kurkuba (03 Nos Habitation) & Srirampur (02 Nos. Habitation) village, Galsi-II Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000564/2020-2021 | 5006/BWD | 10/12/2020 | 10/03/2021 | SUPRIYA RAY | 99.82 | 43.43 | 43.51 | 1
Total | [13 empty] | 104.72 | 43.43 | 41.48