## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Augmentation of BANNABAGRAM Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 400 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including construction of switch room without sanitary arrangements Block-Ausgram-I, District:- Purba-Burdwan. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000074/2022-2023 | 2497/BWD | 13/05/2022 | 13/05/2023 | GHOSH CONCERN | 454.28 | 292.17 | 64.32 | 70
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Laying of pipeline for road crossing due to construction of culvert along PWD Road near Bannabagram Hospital of Bannabagram Piped Water Supply Scheme under Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr,-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000133/2022-2023 | 345/DSD | 30/06/2022 | 30/07/2022 | DUBE ENTERPRISE | 1.07 | 1.07 | 99.88 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of BANANABAGRAM Piped Water Supply Scheme, Block - Ausgram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]_3RD CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000208/2022-2023 | 3297/BWD | 29/07/2022 | 12/09/2022 | ANIRUDDHA FARUQUE | 27.54 | 3.64 | 13.22 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Shifting of UPVC Pipeline due to construction of culvert along PWD Road near Bannabagram Hospital of Bannabagram Piped Water Supply Scheme under Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000463/2021-2022 | 79/DSD | 11/02/2022 | 13/03/2022 | M/S UNIQUE | 2.13 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Route Survey & Preparation of DPR for BANNABAGRAM PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000654/2021-2022 | 101/DSD | 18/02/2022 | 05/03/2022 | SIRCON ENGINEERING SERVICES | 3.09 | 3.09 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Left out part of Laying Distribution system for Augmentation of BANNABAGRAM and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000686/2023-2024 | 4283/BWD | 29/09/2023 | 29/10/2023 | GHOSH CONCERN | 93.7 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Arrear salary (From January'23 to August'23) for the laboratory personnel (Bacteriologist, Laboratory Assistant) of Bonnabagram Subdivision laboratory under Durgapur Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000688/2023-2024 | 754/DSD | 03/10/2023 | 18/10/2023 | CLIFFORD FACILITY SERVICES PVT.LTD. | 0.66 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2021-2022 | 550/BWD | 27/01/2022 |  | Resource Division | 13.66 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 4628/BWD | 17/10/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2021-2022 | 1203/BWD | 04/03/2022 |  | Resource Division | 22.68 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000170/2021-2022 | 1330/BWD | 08/03/2022 |  | Resource Division | 39.95 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000191/2021-2022 | 1373/BWD | 09/03/2022 |  | Resource Division | 3.83 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000238/2021-2022 | 1562/BWD | 15/03/2022 |  | Resource Division | 0.37 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09714 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Bononabagram Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000075/2023-2024 | 2561/CMD | 06/06/2023 | 06/07/2023 | SOUVIK HALDER | 10.98 | 0 | 0 | 0
Total | [13 empty] | 3691.27 | 299.98 | 8.13