## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Contractual Junior Engineer_1,Contractual Junior Engineer_2,Contractual Junior Engineer_3,Contractual Junior Engineer_4,Contractual Junior Engineer_5,JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 20/09/2025 | MANASH GHOSH | 745.87 | 0 | 0 | 1
2 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 1724/E/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 3.95 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways at different TW sites for SHIBADA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000392/2023-2024 | 3218/BWD | 25/07/2023 | 24/07/2024 | ONKAR ENTERPRISE | 319.96 | 195.9 | 61.23 | 71
4 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Repairing of Sajaldhara pipeline(Colony para Uttar) for SIBDA Water Supply Scheme of Aushgram-I Block,under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001102/2023-2024 | 236/DSD | 12/03/2024 | 27/03/2024 | ONKAR ENTERPRISE | 0.97 | 0 | 0 | 100
5 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Sajaldhara pipeline(Colony para Dakshin) for SIBDA Water Supply Scheme of Aushgram-I Block,under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001250/2023-2024 | 242/DSD | 12/03/2024 | 27/03/2024 | ONKAR ENTERPRISE | 0.98 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 4.95 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Material Requisition To Resource Division |  |  | RTOR000307/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 15.17 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Material Requisition To Resource Division |  |  | RTOR000610/2023-2024 | 4915/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 16.68 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Additional quotation for new service connection at Shibda PWSS PH-2 |  |  | BILL/00286/2024-2025 | BP-2024-25-136 | 11/06/2024 | 11/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | New service connection charges for Shibada PWSS TW-1 |  |  | BILL/01706/2023-2024 | BP-2023-24-232 | 20/11/2023 | 20/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.08 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | NEW SERVICE CONNECTION FOR SHIBDA PWSS |  |  | BILL/02469/2023-2024 | BP-2023-24-528 | 13/02/2024 | 13/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 16.79 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 25/12/2024 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME | SM/13492 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Shibada Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000685/2023-2024 | 4014/CMD | 29/08/2023 | 28/09/2023 | S.P. CONSTRUCTION | 29.59 | 18.35 | 62 | 48
Total | [13 empty] | 1267.53 | 214.25 | 16.9