## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram - I,Ausgram - II | Durgapur W/S Division | BHEDIA PIPED WATER SUPPLY SCHEME | SM/14748 | New | Formal Work Order for Additional work for laying 200 mm dia HDPE pipe line and other necessary allied works Amarpur & Bhedia Piped W/S Scheme, Block- Aushgram-2, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2 | ORD/000141/2024-2025 | 1291/DWSD | 06/09/2024 | 05/12/2024 | SAIKAT RAY | 196.61 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram - I,Ausgram - II | Burdwan Division | BHEDIA PIPED WATER SUPPLY SCHEME | SM/14748 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways for BHEDIA Piped Water Supply Scheme under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000807/2023-2024 | 4847/BWD | 09/11/2023 | 08/11/2024 | SUPRIYA RAY | 397.54 | 32.93 | 8.28 | 0
3 | PURBA BARDHAMAN | Ausgram - I,Ausgram - II | Burdwan Division | BHEDIA PIPED WATER SUPPLY SCHEME | SM/14748 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 3.03 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram - I,Ausgram - II | Burdwan Division | BHEDIA PIPED WATER SUPPLY SCHEME | SM/14748 | New | Material Requisition To Resource Division |  |  | RTOR000254/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 14.27 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram - I,Ausgram - II | Burdwan Division | BHEDIA PIPED WATER SUPPLY SCHEME | SM/14748 | New | Material Requisition To Resource Division |  |  | RTOR000603/2023-2024 | 4909/BWD | 10/11/2023 |  | Resource Division | 33.07 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram - I,Ausgram - II | Central Mechanical | BHEDIA PIPED WATER SUPPLY SCHEME | SM/14748 | New | NEW SERVICE CONNECTION FOR BHEDIA PWSS PH-1. |  |  | BILL/03139/2023-2024 | BP-2023-24-649 | 20/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.26 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram - I,Ausgram - II | Central Mechanical | BHEDIA PIPED WATER SUPPLY SCHEME | SM/14748 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram - I,Ausgram - II | Central Mechanical | BHEDIA PIPED WATER SUPPLY SCHEME | SM/14748 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHEDIA Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000826/2023-2024 | 4103/CMD | 29/08/2023 | 28/09/2023 | WEST BENGAL ENGINEERING CO. | 27.76 | 0 | 0 | 0
Total | [13 empty] | 770.8 | 32.93 | 4.27