## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | CHOTO RAMCHANDRAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000377/2023-2024 | 3116/BWD | 19/07/2023 | 15/01/2024 | KALPANA BUILDERS | 150.39 | 55.4 | 36.84 | 10
2 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 0.33 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Material Requisition To Resource Division |  |  | RTOR000308/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 5.69 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Material Requisition To Resource Division |  |  | RTOR000755/2023-2024 | 5244/BWD | 30/11/2023 |  | Resource Division | 18.5 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | New service connection charges for Chhoto Ramchandrapur PWSS TW-1 |  |  | BILL/01486/2023-2024 | BP-2023-24-180 | 04/10/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.92 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | New service connection for Choto Ramchandrapur W/S scheme TW No-2 |  |  | BILL/02276/2023-2024 | BP-2023-24-413 | 19/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.94 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chhoto Ramchandrapur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000688/2023-2024 | 4015/CMD | 29/08/2023 | 28/09/2023 | JAL PRAVAHIKA PVT LTD | 27.77 | 10.84 | 39.02 | 48
Total | [13 empty] | 305.8 | 66.24 | 21.66