## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | SAR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000094/2023-2024 | 2231/BWD | 16/05/2023 | 15/05/2024 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 193.73 | 132.25 | 68.27 | 100
2 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 11.55 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Material Requisition To Resource Division |  |  | RTOR000294/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 12.41 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Material Requisition To Resource Division |  |  | RTOR000758/2023-2024 | 5241/BWD | 30/11/2023 |  | Resource Division | 18.5 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | New service connection charges for Sar PWSS TW-2 |  |  | BILL/01463/2023-2024 | BP-2023-24-162 | 18/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.45 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | New service connection charges for Sar PWSS TW-1 |  |  | BILL/01464/2023-2024 | BP-2023-24-163 | 18/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.8 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sar Water Supply Scheme [ Block-Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000588/2023-2024 | 3924/CMD | 22/08/2023 | 21/09/2023 | D.K. ELECTRIC | 27.75 | 10.79 | 38.86 | 98
Total | [13 empty] | 369.45 | 143.04 | 38.72