## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHUYERA & JALIKANDAR Piped Water Supply Scheme under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000491/2023-2024 | 3509/BWD | 10/08/2023 | 09/08/2024 | MANGES INDUSTRIAL CORPORATION | 950.78 | 0 | 0 | 60
2 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 73.04 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Material Requisition To Resource Division |  |  | RTOR000289/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 16.34 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Material Requisition To Resource Division |  |  | RTOR000615/2023-2024 | 4878/BWD | 10/11/2023 |  | Resource Division | 30.36 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | New service connection charges for Jalkandar PWSS TW-1 |  |  | BILL/01781/2023-2024 | BP-2023-24-290 | 26/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.59 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Quotation for new service connection at Jalikandar W/S Scheme for PH No-2 |  |  | BILL/01824/2023-2024 | BP-2023-24-330 | 03/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.52 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JALKANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000916/2023-2024 | 4180/CMD | 29/08/2023 | 28/09/2023 | SOUNAK ENTERPRISE | 28.48 | 10.96 | 38.48 | 96
9 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & Delivery of Submersible Pumping Machinery for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [Block- AUSGRAM -2] under CMD, PHE Dte.,Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/001623/2023-2024 | 349/DIC/BMSD(D) | 22/12/2023 | 29/12/2023 | H.K. DAS & CO. | 0.8 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & delivery of the following Electrical & Mechanical accessories for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2) under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/001625/2023-2024 | 23/DIC/BMSD(D) | 05/01/2024 | 12/01/2024 | H.K. DAS & CO. | 0.93 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & Installation of Submersible Pumping Machinery, and piping works for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | Driller In-Charge |  | ORD/001628/2023-2024 | 40/DIC/BMSD(D) | 15/01/2024 | 30/01/2024 | H.K. DAS & CO. | 0.38 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & delivery of Electrical & Mechanical accessories for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.· Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/001631/2023-2024 | 45/DIC/BMSD(D) | 19/01/2024 | 26/01/2024 | H.K. DAS & CO. | 0.63 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & Delivery of actuator valve for Tube Well No: 02 at JALKHANDAR Water Supply Scheme [Block- AUSGRAM -2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/001634/2023-2024 | 100/DIC/BMSD(D) | 12/02/2024 | 19/02/2024 | H.K. DAS & CO. | 0.97 | 0 | 0 | 0
Total | [13 empty] | 1208.09 | 10.96 | 0.91