## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi - II | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Shifting of 11KV Line of Mohanpur PWSS under Burdwan Division, PHE Dte. |  |  | BILL/01080/2023-2024 | 1055/JJM | 13/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.33 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi - II | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | MOHANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000386/2023-2024 | 3149/BWD | 20/07/2023 | 19/07/2024 | MD HASIN | 963.53 | 323.53 | 33.58 | 10
3 | PURBA BARDHAMAN | Galsi - II | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Material Requisition To Resource Division |  |  | RTOR000343/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 2.41 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi - II | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Material Requisition To Resource Division |  |  | RTOR000563/2023-2024 | 4937/BWD | 10/11/2023 |  | Resource Division | 54.72 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi - II | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | New service connection for Mohanpur PWSS . |  |  | BILL/02408/2023-2024 | BP-2023-24-506 | 06/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.86 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi - II | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | New service connection for Mohanpur PWSS . |  |  | BILL/02410/2023-2024 | BP-2023-24-507 | 06/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.83 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi - II | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at MOHANPUR Water Supply Scheme [ Block- GALSI-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000792/2023-2024 | 4080/CMD | 29/08/2023 | 28/09/2023 | CHOUDHURY ENTERPRISE | 41.63 | 10.72 | 25.76 | 0
Total | [13 empty] | 1072.31 | 334.25 | 31.17