## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi - I | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | LOAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000419/2023-2024 | 3290/BWD | 31/07/2023 | 30/07/2024 | M/S ASHA CONSTRUCTION | 824.72 | 127.52 | 15.46 | 15
2 | PURBA BARDHAMAN | Galsi - I | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | Material Requisition To Resource Division |  |  | RTOR000395/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 3.72 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi - I | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | Material Requisition To Resource Division |  |  | RTOR000444/2023-2024 | 3845/BWD | 01/09/2023 |  | Resource Division | 164.37 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi - I | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | Material Requisition To Resource Division |  |  | RTOR000560/2023-2024 | 4918/BWD | 10/11/2023 |  | Resource Division | 60.13 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi - I | Central Mechanical | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | NEW SERVICE CONNECTION FOR LOHAPUR PWSS PH-1. |  |  | BILL/03137/2023-2024 | BP-2023-24-651 | 20/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.92 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi - I | Central Mechanical | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2, 3 & 4 at LOAPUR Water Supply Scheme [ Block- Galsi-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000918/2023-2024 | 4182/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 56.97 | 0 | 0 | 0
Total | [13 empty] | 1114.84 | 127.52 | 11.44