## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | BAKSIBAD POGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL |  |  | ORD/000484/2023-2024 | 3504/BWD | 10/08/2023 | 09/08/2024 | M/S PIONEER CONSTRUCTION | 691.24 | 53.26 | 7.7 | 40
2 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Material Requisition To Resource Division |  |  | RTOR000223/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 20.29 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Material Requisition To Resource Division |  |  | RTOR000418/2023-2024 | 3864/BWD | 01/09/2023 |  | Resource Division | 128.72 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram - II | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Material Requisition To Resource Division |  |  | RTOR000644/2023-2024 | 5110/BWD | 23/11/2023 |  | Resource Division | 22.15 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | NEW SERVICE CONNECTION FOR BAKSIBAD PWSS PH-1. |  |  | BILL/03140/2023-2024 | BP-2023-24-652 | 20/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.55 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram - II | Central Mechanical | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | SM/18408 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Baksibad Pogram Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000742/2023-2024 | 4052/CMD | 29/08/2023 | 28/09/2023 | JAGANNATH ENTERPRISE | 29.61 | 0 | 0 | 0
Total | [13 empty] | 999.82 | 53.26 | 5.33