## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi - I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Continuation order for the work of Computer routine maintenance and software's installation including supply of computer peripherals and Stationeries etc. for use office under DWSD, PHE Dte (w.e.f 01.06.2024 to 30.05.2025) | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000025/2024-2025 | 575/DWSD | 22/04/2024 | 22/04/2025 | JOY GURU ENTERPRISE | 3.79 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi - I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Acceptance cum Formal Work Order for Design Engineering Services of Survey, General arrangement drawing, Pile foundation design and drawings, Pipe Pedestal and BOM, Structural design design and drawing, Fabrication drawings for 26 Numbers different dia meter pipe crossing Pipe Bridge at "PURANGAN (Zone-I, II, III), 11 Nos. Mouzas under PURSHA and UCHCHGRAM, SHILLA (Zone-I, II, III, IV), TAHER PUR (Zone-I, II, III) and KHANO (Zone-I and II) sites under Durgapur W/S Division,PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000105/2024-2025 | 1058/DWSD | 25/07/2024 | 23/10/2024 | ASTER CONSULTANCY | 47.43 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi - I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.09.2024 to 28.02.2025 (6 Months)(Sl-03) | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000137/2024-2025 | 1250/DWSD | 30/08/2024 | 26/02/2025 | BIPLAB BANERJEE | 0.82 | 0.4 | 48.49 | 0
4 | PURBA BARDHAMAN | Galsi - I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.03.2024 to 31.08.2024 (6 Months)(Sl-03) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2 | ORD/000296/2023-2024 | 269/DWSD | 29/02/2024 | 27/08/2024 | BIPLAB BANERJEE | 0.82 | 2.2 | 266.77 | 0
5 | PURBA BARDHAMAN | Galsi - I | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Acceptance cum Formal Work Order for the work of Sinking of 3 nos 300 x 200 mm dia T/W 150 mtr and 20Nos 200 x 200 mm dia Riverbank T/W 51 mtr with Construction of P/H cum switch room chlorine room at Uchagram under 11 nos mouzas PWSS (JJM), Block:- Galsi-I, Dist- Purba Bardhaman. | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2 | ORD/000310/2023-2024 | 373/DWSD | 15/03/2024 | 13/06/2024 | S & P ENTERPRISE | 72.51 | 17.13 | 23.62 | 0
6 | PURBA BARDHAMAN | Galsi - I | Burdwan Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Piped Water Supply Scheme for different Mouzas works related (LDSs, Rising Mains, FHTCs, Constn. CWR, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] (For Pursha, Uchhagram & Rampur Jurisdiction) |  |  | ORD/000475/2023-2024 | 3761/BWD | 29/08/2023 | 28/08/2024 | S & P ENTERPRISE | 1827.37 | 198.07 | 10.84 | 35
7 | PURBA BARDHAMAN | Galsi - I | Burdwan Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 30/03/2024 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 5.67 | 5 | 20
8 | PURBA BARDHAMAN | Galsi - I | Central Mechanical | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | SM/18679 | New | Providing Electro-mechanical accessories and others for Sub-Surface Water based Piped Water Supply Scheme for 11 Nos Mouza under Galsi-I Block, Purba Bardhaman. |  |  | ORD/001210/2023-2024 | 18/CMD | 03/01/2024 | 28/12/2024 | SINHA ELECTRICALS | 132.25 | 0 | 0 | 0
Total | [13 empty] | 2198.34 | 223.46 | 10.17