## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Gangatikuri PWSS | SM/06750 | Retrofitting | Supply of 10 mm NB Gun-Metal Ferrule conforming to IS:2692-1989 for water tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-4] |  |  | ORD/000108/2021-2022 | 3186/BWD | 08/06/2021 | 08/07/2021 | R.K. INDUSTRIES | 76.05 | 20.36 | 26.77 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Gangatikuri PWSS | SM/06750 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of GANGATIKURI Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000706/2020-2021 | 1007/BWD | 05/02/2021 | 06/05/2021 | M/S ASOKE GHOSH & BROTHERS | 47.52 | 29.44 | 61.96 | 1
Total | [13 empty] | 123.57 | 49.8 | 40.3