## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | SM/06768 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Sahapur (Pt-B) village of Purba Sahapur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 7B] | Assistant Engineer |  | ORD/000131/2020-2021 | 2584/BWD | 09/07/2020 | 08/08/2020 | SETH ENTERPRISE | 4.92 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | SM/06768 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Sahapur (Pt-A) village of Purba Sahapur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 7A] | Assistant Engineer |  | ORD/000132/2020-2021 | 2585/BWD | 09/07/2020 | 08/08/2020 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.92 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | SM/06768 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-A) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : ¿11A¿] (Agreement no.-501/BWD of 2020-21) | Assistant Engineer |  | ORD/000145/2020-2021 | 4083/BWD | 16/10/2020 | 15/11/2020 | RAINBOW CONSTRUCTION | 2.23 | 2.23 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | SM/06768 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 03 Nos. Piped W/S. Schemes under Kalna II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000336/2024-2025 | 3016/BWD | 05/08/2024 | 25/08/2024 | HORIZEN | 7.55 | 1.26 | 16.7 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | SM/06768 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur, Char Sahapur and Natungram village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-789/BWD/2020-21) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000517/2020-2021 | 365/KTS | 15/12/2020 | 22/12/2020 | DUBE ENTERPRISE | 2.46 | 2.46 | 99.77 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | SM/06768 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Part-B) village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-497/BWD/2020-21) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000547/2020-2021 | 4007/BWD | 14/10/2020 | 13/11/2020 | DUBE ENTERPRISE | 2.84 | 2.84 | 100 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | SM/06768 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Sahapur (Pt-B) village of Purba Sahapur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 7B] | Assistant Engineer |  | ORD/000738/2020-2021 | 2587/BWD | 04/08/2020 | 03/09/2020 | SETH ENTERPRISE | 4.92 | 4.92 | 100 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | SM/06768 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | Assistant Engineer |  | ORD/000867/2020-2021 | 4318/BWD | 04/11/2020 | 14/11/2020 | MD HASIN | 4.93 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | SM/06768 | Retrofitting | Extension of pipeline at Purbasahapur mouza under Purbasahapur water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Sl-A] | Assistant Engineer |  | ORD/000930/2020-2021 | 29/KSD | 11/01/2021 | 25/02/2021 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.84 | 4.73 | 97.59 | 1
Total | [13 empty] | 39.61 | 18.43 | 46.53