## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS | SM/06770 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MADANAGAR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000063/2023-2024 | 1935/BWD | 24/04/2023 | 24/05/2023 | S.C. ENTERPRISE | 20.87 | 9.45 | 45.27 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS | SM/06770 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madanagar habitation of Madanagar piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Tr No.-531/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000199/2020-2021 | 3741/BWD | 07/10/2020 | 06/11/2020 | PABITRA KUMAR SAMANTA | 4.92 | 4.92 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS | SM/06770 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000344/2021-2022 | 39/BWD | 05/01/2022 | 04/02/2022 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS | SM/06770 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madanagar (Part) village (Madanagar Mejhpur Habitation) of Madanagar piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000605/2020-2021 | 69/BWD | 05/01/2021 | 20/01/2021 | PABITRA KUMAR SAMANTA | 4.86 | 4.05 | 83.32 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS | SM/06770 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madanagar village of Madanagar piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-716/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000651/2020-2021 | 1224/BWD | 11/02/2021 | 13/03/2021 | PABITRA KUMAR SAMANTA | 3.76 | 3.76 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS | SM/06770 | Retrofitting | Restore of damaged Pipeline at Madanagar Dakshin Para under MADANAGAR Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001051/2023-2024 | 823/BWD | 28/02/2024 | 29/03/2024 | UTPAL NANDI | 6.18 | 0 | 0 | 0
Total | [13 empty] | 56.22 | 22.19 | 39.46