## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Construction of boundary wall at Pump house no - 3 Site of Hatgobindapur Water Supply Scheme under Bardhaman-II Dev. Block of Burdwan Division, PHE Dte. (Length -40.00 Mtr, Col-16 Nos). Group : B | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000052/2022-2023 | 701/BSD | 27/04/2022 | 11/06/2022 | ANIRUDDHA FARUQUE | 2.61 | 2.61 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of HATGOBINDAPUR Piped Water Supply Scheme and its adjoining mouzas at Burdwan - II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000054/2022-2023 | 2232/BWD | 29/04/2022 | 29/05/2022 | M/S ASHA CONSTRUCTION | 19.32 | 18.67 | 96.63 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Additional work for Construction of boundary wall at Pump house no - 3 Site of Hatgobindapur Water Supply Scheme under Bardhaman-II Dev. Block of Burdwan Division, PHE Dte. (Length -18.00 Mtr, Col-2 Nos). Group - A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000061/2022-2023 | 722/BSD | 02/05/2022 | 01/06/2022 | MOHAMMAD ISSA | 1.48 | 1.48 | 99.61 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Left out FHTC (Hatgobindapur, Banagram, Ramnagar & Hatkanda village) of HATGOBINDAPUR PWSS under Burdwan-II Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000116/2023-2024 | 2302/BWD | 19/05/2023 | 18/06/2023 | M/S SAYAN CHAKRABORTY | 9.6 | 9.63 | 100.32 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village (Part) of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 01] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000122/2021-2022 | 4390/BWD | 31/08/2021 | 15/09/2021 | M/S ASHA CONSTRUCTION | 4.86 | 3.48 | 71.68 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6A¿] (T.R. No. 156/BWD/2020-21) |  |  | ORD/000152/2020-2021 | 2743/BWD | 10/08/2020 | 09/09/2020 | M/S ASHA CONSTRUCTION | 4.92 | 4.92 | 100 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Banagram village of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6B¿] (T.R. No.-155/BWD/2020-21) |  |  | ORD/000153/2020-2021 | 2744/BWD | 10/08/2020 | 09/09/2020 | M/S ASHA CONSTRUCTION | 4.92 | 4.92 | 100 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 3rd tube well site (Size-3.60 mtr x 3.00 mtr) for HATGOBINDAPUR water supply scheme under Burdwan-II development Block under Burdwan Sub-Division, under Burdwan Division, PHE Dte.[Gr.-A] |  |  | ORD/000211/2021-2022 | 665/BSD | 07/06/2021 | 22/07/2021 | KAJAL MUKHERJEE | 2.76 | 2.71 | 98.16 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Providing left out FHTC for 100% covarage in different village within Hatgobindapur PWSS , Bardhhaman-II Development Block under Burdwan Division, PHE Dte |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000293/2024-2025 | 1275/BSD | 12/07/2024 | 26/08/2024 | PAL CONSTRUCTION | 4.78 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village of Hatgobindapur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-317/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000347/2020-2021 | 3702/BWD | 05/10/2020 | 04/11/2020 | M/S ASHA CONSTRUCTION | 4.92 | 4.92 | 100 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000416/2021-2022 | 385/BWD | 20/01/2022 | 19/02/2022 | BISWAS ENTERPRISE | 11.97 | 3.71 | 30.99 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village (Part) of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 01] |  |  | ORD/000465/2020-2021 | 1413/BWD | 18/02/2021 | 05/03/2021 | M/S ASHA CONSTRUCTION | 4.86 | 4.86 | 100 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Extension of UPVC distribution pipeline in connection with FHTC for Hatgobindapur and its adjoining mouzas water supply scheme at Bardhaman-II Development Block under Burdwan Division, PHE Dte.[Gr-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000688/2021-2022 | 989/BSD | 30/07/2021 | 29/08/2021 | M/S ASHA CONSTRUCTION | 4.82 | 4.74 | 98.35 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Laying of interconnection of the Pump No.-3 with distribution line 100 mm dia for Hatgobindapur piped water supply scheme of Burdwan-II Block under Burdwan Division, PHE Dte.[Gr.-B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000702/2021-2022 | 1027/BSD | 05/08/2021 | 04/09/2021 | ANWESHA CONSTRUCTION | 1.67 | 1.5 | 90.23 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Sinking of additional Tube well 250 x 200 mm dia Tube well 150 mtr depth by D.R. Rig method using UPVC pipe (CD) and fibre glass strainer for Hatgobindapur piped water supply scheme (3rd tube well site), Block-Burdwan-II under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000982/2020-2021 | 1493/BWD | 18/02/2021 | 20/03/2021 | C.M. ENTERPRISE | 8.68 | 6.99 | 80.57 | 1
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 6800/BWD | 07/12/2021 |  | Resource Division | 2.85 | 0 | 0 | 0
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | SM/06971 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001246/2021-2022 | 900/DW | 03/02/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 34.54 | 0 | 0 | 0
Total | [13 empty] | 129.55 | 75.14 | 58