## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nandra village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-176/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000102/2020-2021 | 2735/BWD | 10/08/2020 | 09/09/2020 | BHARAT CONSTRUCTION | 4.92 | 9.84 | 200 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur & Dangachha village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-177/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000103/2020-2021 | 2736/BWD | 10/08/2020 | 09/09/2020 | BHARAT CONSTRUCTION | 4.92 | 9.84 | 200 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Providing FHTC (130 nos.) and Extension of UPVC dist. Pipeline at Noapara, Pirtala ,Nandra village of NANDRA water supply scheme at Burdwan-II Block under Burdwan Division PHE Dte..Gr. I | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000213/2021-2022 | 1479/BSD | 09/11/2021 | 09/12/2021 | BHARAT CONSTRUCTION | 4.81 | 4.81 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Providing FHTC in Nandra & Naopara village for 100% coverage in Sajal Gram from existing distribution system within NANDRA PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Gr.F. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000339/2022-2023 | 1360/BSD | 03/08/2022 | 08/08/2022 | BHARAT CONSTRUCTION | 0.97 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000416/2021-2022 | 385/BWD | 20/01/2022 | 19/02/2022 | BISWAS ENTERPRISE | 11.97 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/07/2025 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur & Dangachha village of Nandra Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿10B¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000463/2020-2021 | 4085/BWD | 16/10/2020 | 15/11/2020 | BHARAT CONSTRUCTION | 1.65 | 3.3 | 200 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Providing FHTC in Nandra & Naopara village for 100% coverage in Sajal Gram from existing distribution system within Nandra PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000654/2022-2023 | 1360-A/BSD | 03/08/2022 | 08/08/2022 | BHARAT CONSTRUCTION | 0.97 | 0.96 | 99.6 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nandra village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000714/2020-2021 | 4087/BWD | 16/10/2020 | 15/11/2020 | BHARAT CONSTRUCTION | 2 | 4 | 200 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | SM/07205 | Retrofitting | Additional Extension of UPVC distribution pipeline in connection with FHTC for NANDRA & adjoining mouzas water supply scheme at Bardhaman-I Block under Burdwan division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000743/2020-2021 | 73/BSD | 19/01/2021 | 18/02/2021 | BHARAT CONSTRUCTION | 4.22 | 8.37 | 198.26 | 1
Total | [13 empty] | 346.03 | 41.13 | 11.89