## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme | SM/07546 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Enayatpur and Sankhai village under UDDHARANPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | Assistant Engineer |  | ORD/000140/2021-2022 | 589/KTS | 06/09/2021 | 06/10/2021 | M/S S. CHOUDHURY | 4.85 | 4.85 | 99.97 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme | SM/07546 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Uddharanpur village under UDDHARANPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-2) | Assistant Engineer |  | ORD/000141/2021-2022 | 590/KTS | 06/09/2021 | 06/10/2021 | M/S S. CHOUDHURY | 4.83 | 4.82 | 99.79 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme | SM/07546 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Naihati village under UDDHARANPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-3) | Assistant Engineer |  | ORD/000142/2021-2022 | 591/KTS | 06/09/2021 | 06/10/2021 | M/S S. CHOUDHURY | 4.83 | 4.81 | 99.54 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme | SM/07546 | Retrofitting | Special maintenance and construction of sluice Valve chamber at Uddharanpur Piped water Supply Scheme at Ketugram-II Block, under Katwa Sub-Division within Burdwan Division PHE Dte.[Sl No-1] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000369/2023-2024 | 610/KTS | 19/06/2023 | 19/07/2023 | BABUL SK | 0.97 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme | SM/07546 | Retrofitting | Special maintenance and construction of sluice Valve chamber at Uddharanpur Piped water Supply Scheme at Ketugram-II Block, under Katwa Sub-Division within Burdwan Division PHE Dte.[Sl No-2] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000370/2023-2024 | 611/KTS | 19/06/2023 | 19/07/2023 | BABUL SK | 0.97 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme | SM/07546 | Retrofitting | Special maintenance and construction of sluice Valve chamber at Uddharanpur Piped water Supply Scheme at Ketugram-II Block, under Katwa Sub-Division within Burdwan Division PHE Dte.[Sl No-3] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000371/2023-2024 | 633/KTS | 19/06/2023 | 19/07/2023 | BABUL SK | 0.76 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme | SM/07546 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Uddharanpur Piped Water Supply Scheme at Enayetpur, Naihati, Sankhai, Sitahati & Uddharanpur (1 No Habitation) Village (Mouza), Ketugram-II Block under Burdwan Division, PHE Dte. (Agreement No. 97/SE/CC/PHE/Dte of 2020-2021) | Assistant Engineer |  | ORD/000416/2020-2021 | 913/BWD | 02/02/2021 | 03/04/2021 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 86.77 | 47.93 | 55.25 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme | SM/07546 | Retrofitting | Drinking water supply to 10 Nos ICDS for Uddharanpur water supply scheme Ketugram-II Block under Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000961/2020-2021 | 36/KTS | 18/01/2021 | 17/02/2021 | MAA KHEPIMAYER CHARANE | 4.79 | 0 | 0 | 1
Total | [13 empty] | 108.76 | 62.41 | 57.38