## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block | SM/07797 | Retrofitting | Providing 22 Nos.FHTC at IDILPUR & FAKIRPUR village for declearation of SWAJALGRAM under FAKIRPUR Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000166/2024-2025 | 1035/BSD | 10/06/2024 | 10/07/2024 | IMPULSE INTERNATIONAL | 0.75 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block | SM/07797 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC)for Swajal Gram from existing distribution system within the command area of Idilpur & Fakirpur village under Fakirpur Piped W/S.Scheme under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr. I | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000346/2022-2023 | 1380/BSD | 05/08/2022 | 10/08/2022 | BAMDEB CONSTRUCTION & CO | 0.96 | 0.96 | 100 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block | SM/07797 | Retrofitting | Construction of boundary wall at Head works site of Fakirpur water supply scheme under Bardhaman-I Block under Burdwan Division, PHE Dte.[Length-50.20 Mtr][Part-B][South & West Side][Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000558/2021-2022 | 1026/BSD | 05/08/2021 | 19/09/2021 | AYSAN KHAN | 3.77 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block | SM/07797 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of FAKIRPUR Piped Water Supply Scheme at Fakirpur & Bongpur village (Mouza), Burdwan - I Block under Burdwan Division, PHE Dte._2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000641/2020-2021 | 355/BWD | 15/01/2021 | 01/03/2021 | AYSAN KHAN | 36.69 | 18.91 | 51.53 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block | SM/07797 | Retrofitting | Providing Balance Functional Household Tap Connection(FHTC)for Swajal Gram from existing distribution system within the command area of Idilpur & Fakirpur Village under of FAKIRPUR W.S.Scheme of Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000847/2022-2023 | 1380-A/BSD | 05/08/2022 | 10/08/2022 | BAMDEB CONSTRUCTION & CO | 0.96 | 0 | 0 | 0
Total | [13 empty] | 43.13 | 19.86 | 46.05