## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block | SM/07803 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati village of Jalahati piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-768/BWD/2020-21) | Assistant Engineer |  | ORD/000387/2020-2021 | 4793/1/BWD | 03/12/2020 | 02/01/2021 | SETH ENTERPRISE | 4.92 | 4.92 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block | SM/07803 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati (P) village (Jalahati (P) habitation) of Jalahati Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 26] | Assistant Engineer |  | ORD/000413/2020-2021 | 1462/BWD | 18/02/2021 | 05/03/2021 | BARDHAMAN AQUA ENGINEERING | 4.86 | 4.86 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block | SM/07803 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati (P) village (Beltalapara habitation) of Jalahati Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B). [SL. No. : 25] | Assistant Engineer |  | ORD/000414/2020-2021 | 1464/BWD | 18/02/2021 | 05/03/2021 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.86 | 4.86 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block | SM/07803 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati (P)village (Beltalapara habitation) of Jalahati Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A). [SL. No. : 24] | Assistant Engineer |  | ORD/000415/2020-2021 | 1465/BWD | 18/02/2021 | 05/03/2021 | SETH ENTERPRISE | 4.82 | 4.86 | 100.9 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block | SM/07803 | Retrofitting | Providing 350 Nos. FHTC work at JALAHATI W/S scheme for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification) within Purbasthali-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000800/2022-2023 | 1520/BWD | 28/03/2023 | 27/04/2023 | IYASIN DAFADAR | 14.47 | 13.57 | 93.78 | 0
Total | [13 empty] | 33.94 | 33.08 | 97.47