## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block | SM/07805 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga & Sarisha village and North Jhaudwnga (Part) & Sarisha habitation of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-554/BWD/2020-21) | Assistant Engineer |  | ORD/000256/2020-2021 | 4114/BWD | 16/10/2020 | 15/11/2020 | BARABELUN NO.-II G.P. UNEMPLOYED CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.86 | 4.86 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block | SM/07805 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000338/2024-2025 | 3018/BWD | 05/08/2024 | 24/09/2024 | HORIZEN | 23.7 | 0 | 0 | 10
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block | SM/07805 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga village and North Jhaudanga (Part) habitation of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-761/BWD/2020-21) | Assistant Engineer |  | ORD/000372/2020-2021 | 4113/BWD | 16/10/2020 | 15/11/2020 | BARDHAMAN AQUA ENGINEERING | 4.86 | 4.86 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block | SM/07805 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga village and North Jhaudanga (Part) habitation of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-762/BWD/2020-21) | Assistant Engineer |  | ORD/000373/2020-2021 | 4795/BWD | 03/12/2020 | 02/01/2021 | BARDHAMAN AQUA ENGINEERING | 3.51 | 3.51 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block | SM/07805 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga village (Jhaudanga south habitation) of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-868/BWD/2020-21) | Assistant Engineer |  | ORD/000612/2020-2021 | 597/BWD | 25/01/2021 | 09/02/2021 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.86 | 4.86 | 100 | 1
Total | [13 empty] | 41.78 | 18.08 | 43.28