## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Vehicle bill (Car No.-WB-41H-3668) for the month of July to September'2023. |  |  | BILL/01679/2023-2024 | 1142/JJM | 29/12/2023 |  | MD HASIN | 0.86 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ORGRAM Piped Water Supply Scheme & Sibda Colony habitation, Bhatar Block under Burdwan Division, PHE Dte.(Agreement No. 59/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000123/2020-2021 | 4886/BWD | 07/12/2020 | 07/03/2021 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 97.01 | 28.41 | 29.28 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Extension of distribution main for providing FHTC at Shalkuni village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000288/2021-2022 | 717/DSD | 17/12/2021 | 16/01/2022 | DHIRENDRANATH SOM | 3.62 | 3.62 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Extension of distribution main for providing FHTC at Shilakot village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte.[Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000289/2021-2022 | 718/DSD | 17/12/2021 | 16/01/2022 | DHIRENDRANATH SOM | 3.15 | 3.1 | 98.48 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Extension of distribution main for providing FHTC at Shikarpur village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000290/2021-2022 | 719/DSD | 17/12/2021 | 16/01/2022 | DHIRENDRANATH SOM | 3.28 | 3.28 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ORGRAM Piped Water Supply Scheme at Salkuni, Orgram (10 Nos Habitation), & Silakote Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte._2ND CALL.(Agreement no. 102/SE/CC/PHE/Dte of 2020-2021) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000424/2020-2021 | 1086/BWD | 08/02/2021 | 09/05/2021 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 81.92 | 40 | 48.83 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for Orgram (Zone-I) & it's adjoining mouzas W/S. scheme under Burdwan Division, P.H.E. Dte.Ref. Drawing No.PC-I/OHR/7/2012 Dated 07.06.2012. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000448/2021-2022 | 764/BWD | 07/02/2022 | 06/08/2022 | S.N. ENTERPRISE | 67.98 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Shifting and relaying of Distribution system and Rising main at OHR site of Orgram Piped W/S Scheme (Zone-II) at Bhatar Block under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000566/2023-2024 | 655/DSD | 24/08/2023 | 23/09/2023 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | SM/07814 | Retrofitting | Extension of pipeline at Bagmara village of Orgram (Z-II) and its adjoining mouzas piped water supply scheme at Bhatar Block within Burdwan Sadar Sub-Division, under Burdwan Division, PHE Dte.[Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000781/2021-2022 | 952/BSD | 23/07/2021 | 22/08/2021 | M/S S. CHOUDHURY | 2.01 | 0 | 0 | 1
Total | [13 empty] | 260.57 | 78.41 | 30.09