## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Basantaput and Paratal village within the command area of HIRANYAGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : B] | AE(HQs) |  | ORD/000041/2022-2023 | 228/AE/HQ | 19/04/2022 | 19/05/2022 | M/S UNIQUE | 4.77 | 4.66 | 97.6 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Construction of boundary wall (North-East Side) at Headworks site of HIRANYAGRAM W/S Scheme under Jamalpur Block of Burdwan Division, PHE Dte. (Length-63Mtr., Column-26Nos.) [Group : E] | AE(HQs) |  | ORD/000044/2022-2023 | 237/AE/HQ | 19/04/2022 | 19/05/2022 | APORUPA CONSTRUCTION | 4.83 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Basantapur and Ruda village within the command area of HIRANYAGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : B] | AE(HQs) |  | ORD/000046/2022-2023 | 200/AE/HQ | 06/04/2022 | 06/05/2022 | DEY NIRMAN | 4.85 | 4.35 | 89.75 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Paratal village within the command area of HIRANYAGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : C] | AE(HQs) |  | ORD/000047/2022-2023 | 201/AE/HQ | 06/04/2022 | 06/05/2022 | M/S SAYAN CHAKRABORTY | 4.85 | 4.84 | 99.84 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Laying of 75mm and 50mm dia. uPVC pipe for providing FHTC at different habitation of Paratal and Ruda Mouza within Hiranyagram Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E DTE. [Group: ¿B¿] | AE(HQs) |  | ORD/000223/2021-2022 | 1818/AE/HQ | 21/09/2021 | 21/10/2021 | APORUPA CONSTRUCTION | 4.74 | 4.44 | 93.71 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Hiranyagram Piped Water Supply Scheme at Ruda Village (2 Nos. habitations), Hiranyagram Village (2 Nos. habitations), Sajipur Village, Basantapur Village (2 Nos. habitations), Parutal Village (2 Nos. habitations), Betragarh Village, Jamalpur Block under Burdwan Division, PHE Dte.[Agreement No. 711/BWD OF 2020-2021.] | AE(HQs) |  | ORD/000336/2020-2021 | 1597/BWD | 22/02/2021 | 23/04/2021 | MANASH GHOSH | 93.36 | 92.7 | 99.29 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Construction of balance portion of boundary wall at H/W SITE of HIRANYAGRAM Piped W/S. Scheme under Burdwan Division PHE Dte. [Group : C] | AE(HQs) |  | ORD/000360/2022-2023 | 447/AE/HQ | 16/08/2022 | 15/09/2022 | APORUPA CONSTRUCTION | 2.98 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Construction of valve chamber and necessary repairing work of pipeline for smooth running of HIRANYAGRAM Piped Water Supply Scheme, Jamalpur Dev. Block under Burdwan Division, P.H.E Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000402/2023-2024 | 387/AE/HQ | 26/07/2023 | 25/08/2023 | SANDIPAN SENGUPTA | 0.74 | 0.74 | 99.89 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Hiranyagram village within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : B] | AE(HQs) |  | ORD/000459/2021-2022 | 67/AE/HQ | 11/02/2022 | 13/03/2022 | APORUPA CONSTRUCTION | 4.83 | 4.62 | 95.68 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Supplying, fitting & fixing of iron gate, including construction of 125mm thick wall & concrete floor at H/W site of HIRANYAGRAM PWSS under Burdwan Division PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000528/2023-2024 | 755/AE/HQ | 21/08/2023 | 20/09/2023 | PAPRI HAZRA | 4.36 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Laying of uPVC pipe for providing FHTC at Ruda, Sajipur, Paratal, Betragar Village within Hiranyagram Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-D | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000629/2021-2022 | 126/AE/HQ | 04/03/2022 | 19/03/2022 | APORUPA CONSTRUCTION | 4.64 | 3 | 64.71 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Continuation order for supply & delivery of different dia CIDF pipes, sluice valve & fittings for construction of RCC OHR (450 cum capacity) for Hiranyagram w/s scheme under Burdwan Division, PHE Dte. | AE(HQs) |  | ORD/000692/2021-2022 | 388/BWD | 20/01/2022 | 09/02/2022 | ASHOKE ENGINEERING WORKS | 15.17 | 0 | 0 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 5525/BWD | 23/12/2022 |  | Resource Division | 0.62 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | SM/07818 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Head Quarters, Burdwan Division, PHE Dte. for the month of June & July'22. |  |  | VCH/000493/2022-2023 | 460/VEH/22-23 | 29/08/2022 |  | SK. ASRAFUDDIN | 0.76 | 0 | 0 | 0
Total | [13 empty] | 151.49 | 119.34 | 78.78