## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing left out FHTC for Putunda village within SUHARI PWSS , Bardhhaman-II Development Block under Burdwan Division, PHE Dte |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000144/2024-2025 | 1032/BSD | 10/06/2024 | 10/07/2024 | ISHAN CONSTRUCTION | 0.96 | 0.48 | 49.29 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Allied work for inter connection between 3rd tube well site and laying distribution system for Suhari PWSS within Bardhaman-II Block , under Burdwan Division, PHE Dte |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000292/2024-2025 | 1274/BSD | 12/07/2024 | 19/07/2024 | ISHAN CONSTRUCTION | 2.34 | 1.17 | 50 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing FHTC (650 Nos.) from dist. System within the command area of SUHARI piped water supply scheme at Masjidpara, Allahadipara, Varpally, Saktigarh Utttar Bazar Habitation (Putunda & Saktigarh Mouza) at Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000294/2021-2022 | 7027/BWD | 17/12/2021 | 16/01/2022 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 19.58 | 19.58 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing FHTC in Jarul village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-A). Gr.K. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000347/2022-2023 | 1381/BWD | 05/08/2022 | 10/08/2022 | SAMANTA CONSTRUCTION | 0.96 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing FHTC in Jarul village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-B).Gr.L. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000348/2022-2023 | 1382/BSD | 05/08/2022 | 10/08/2022 | SAMANTA CONSTRUCTION | 0.96 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing FHTC in Shuhari village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-A).Gr.M. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000349/2022-2023 | 1383/BSD | 05/08/2022 | 10/08/2022 | SAMANTA CONSTRUCTION | 0.97 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing FHTC in Shuhari village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-B). Gr.N. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000350/2022-2023 | 1384/BSD | 05/08/2022 | 10/08/2022 | SAMANTA CONSTRUCTION | 0.96 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing FHTC in Atagar village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Gr.O. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000351/2022-2023 | 1390/BSD | 08/08/2022 | 13/08/2022 | SAMANTA CONSTRUCTION | 0.56 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000416/2021-2022 | 385/BWD | 20/01/2022 | 19/02/2022 | BISWAS ENTERPRISE | 11.97 | 1.5 | 12.5 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Suhari piped water supply scheme at Putunda, Atagarh (08 Nos. Habitation), Ghatshila (04 Nos. Habitation), Jarur (02 Nos. Habitation), Saiadpur Chak, Tajpur (04 Nos. Habitation) village, Bardhaman-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000529/2020-2021 | 5004/BWD | 10/12/2020 | 10/03/2021 | NATIONAL CONSTRUCTION | 80.78 | 15.48 | 19.16 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing FHTC for 100% coverage in different village (SUHARI, JARUL, ATTAGAR & GHATSHILA) from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000572/2023-2024 | 3722/BWD | 25/08/2023 | 24/09/2023 | BIPLAB SAMANTA | 18.91 | 8.29 | 43.84 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Krishnapur village of Suhari piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000677/2020-2021 | 1326/BWD | 12/02/2021 | 14/03/2021 | SAMANTA CONSTRUCTION | 4.92 | 3.5 | 71.18 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for SUHARI its Adjoining Mouza W/S Scheme, Block -Bardhaman-II within Burdwan Sub-Division, PHE Dte. (Mouza- PURBA KRISHNAPUR) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000767/2022-2023 | 502/BSD | 21/03/2023 | 05/05/2023 | M/S PALASH BISWAS | 3.45 | 2.83 | 81.92 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Tajpur Village, Burdwan - II Block within Suhari PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000773/2023-2024 | 853/AE/HQ | 06/11/2023 | 06/12/2023 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 95.4 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | SM/07823 | Retrofitting | Providing laying distribution pipe line due to shal balla pileing at Sontoshpur village by P.Samiti for SUHARI PWSS at Bardhhaman-II Development Block under Burdwan Division,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001178/2023-2024 | 537/BSD | 14/03/2024 | 13/04/2024 | M/S PALASH BISWAS | 0.89 | 0.44 | 49.66 | 100
Total | [13 empty] | 148.98 | 53.98 | 36.23