## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for MAHESHDANGA Piped Water Supply Scheme, Block - Memari - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000072/2022-2023 | 2472/BWD | 12/05/2022 | 11/06/2022 | NADIA TUBEWELLS | 10.32 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Laying of 200 mm dia HDPE distribution pipe line (Node No-402 To 401B) for Mahesdanga & ADJOINING MOUZAS WATER SUPPLY SCHEME at Memari-I Development Block under Burdwan Division, PHE Dte. Group : C | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000082/2022-2023 | 816/BSD | 20/05/2022 | 19/06/2022 | M/S ASHA CONSTRUCTION | 4.79 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Laying of 200mm.dia. HDPE Distribution pipe line(Node No.401B to 401)for MAHESHDANGA & adjoining mouzas Water Supply Scheme at Memari-I Development block under Burdwan Division,PHE Dte. Group - D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000091/2022-2023 | 831/BSD | 23/05/2022 | 22/06/2022 | M/S ASHA CONSTRUCTION | 4.49 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Construction of boundary wall including land development at 2nd Tube Well site of MAHESHDANGA water supply scheme under Memari-I Block of Burdwan Division, PHE Dte. (Length -52.00 Mtr, Col-20 Nos). " Group : C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000106/2022-2023 | 985/BSD | 16/06/2022 | 31/07/2022 | MAA MAHAMAYA CONSTRUCTION | 3.46 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maheshdanga Piped Water Supply Scheme at Salda Village (2 Nos. habitations) & Bahara Village (5 Nos. habitations), Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000156/2021-2022 | 4634/BWD | 09/09/2021 | 08/11/2021 | CREATION CONSTRUCTION | 52.73 | 52.53 | 99.62 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Canal crossing of Mahesdanga water supply scheme(Node point 192 to 193) under Memari-I Block under Burdwan Division, PHE Dte.[Gr.-D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000313/2021-2022 | 1158/BSD | 31/08/2021 | 30/09/2021 | RANADHIR SINHA | 4.85 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maheshdanga Piped Water Supply Scheme at Maheshdanga Village (5 Nos. habitations) & Kathalgachhi Village (3 Nos. habitations), Memari ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 722/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000324/2020-2021 | 1687/BWD | 24/02/2021 | 25/04/2021 | PABITRA KUMAR SAMANTA | 54.78 | 56.41 | 102.98 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Construction of boundary wall (SOUTH side) at Pump house no - I Site of Maheshdanga Water Supply Scheme under Memari-I Dev. Block of Burdwan Division, PHE Dte. (Length -58.00 Mtr, Col-21 Nos). Gr. G | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000475/2021-2022 | 280/BSD | 15/02/2022 | 01/04/2022 | SK ABDUL HALIM | 4.19 | 0 | 0 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Construction of 168 Mtr long P.C.C Approach road from Main Road to OHR site and inside boundary of OHR Site of MAHESHDANGA PWSS under Memari-I Development Block under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000530/2023-2024 | 3627/BWD | 21/08/2023 | 20/09/2023 | MANAS BHATTACHARYA | 5.95 | 5.3 | 89.16 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Providing FHTC from dist. System within the command area of MAHESDANGA Piped Water Supply Scheme at Bahera (Part) and Mahesdanga (Part) Village (Mahesdanga, Aymadeulepara, Kamarpara & Jangalpara Habs.) at Memari-I Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000611/2021-2022 | 1571/BWD | 16/03/2022 | 15/04/2022 | SUPRIYA RAY | 22.42 | 22.4 | 99.94 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Providing FHTC from dist. System within the command area of MAHESDANGA Piped Water Supply Scheme at Deule Village, Salda Village, Bhara Village, Kathalgachi Village & Koleypara Village at Memari-I Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000613/2021-2022 | 1573/BWD | 16/03/2022 | 15/05/2022 | SUPRIYA RAY | 70.5 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maheshdanga Piped Water Supply Scheme at Deule Village (4 Nos. habitations), Memari ¿ I Block under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000638/2020-2021 | 1796/A/BWD | 26/02/2021 | 12/04/2021 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 27.66 | 27.65 | 99.96 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Construction of boundary wall (North side) including Front Gate at Pump house no - I Site of Maheshdanga Water Supply Scheme under Memari-I Dev. Block of Burdwan Division, PHE Dte. (Length -55.00 Mtr, Col-20 Nos). Gr.D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000647/2021-2022 | 469/BSD | 21/03/2022 | 05/05/2022 | SK ABDUL HALIM | 4.37 | 0 | 0 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Earth work in excavation including shoring work of 700 cum capacity 20 Mtr staging height RCC Over Head Reservoir of Mahesdanga water supply scheme of Memari-I Block under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000770/2021-2022 | 1365/BSD | 05/10/2021 | 10/10/2021 | SK ALIM | 4.73 | 0 | 0 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Earth filling and sand filling in excavated portion and land development at Head work site of 700 cum capacity 20 Mtr staging height RCC Over Head Reservoir of Mahesdanga water supply scheme of Memari-I Block under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000773/2021-2022 | 1408/BSD | 08/10/2021 | 13/10/2021 | M/S PROCHESTA ENTERPRISE | 4.14 | 0 | 0 | 1
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Replacement of fully damaged PVC water supply line at Dulepara along National Highway for MAHESDANGA and its adj.mouza W/S Scheme,Block:Memari-I within Burdwan Sub-Division,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000870/2023-2024 | 2746/BSD | 28/11/2023 | 28/12/2023 | SUPRIYA RAY | 0.96 | 0 | 0 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 421/BWD | 20/01/2022 |  | Resource Division | 5.49 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | SM/07855 | Retrofitting | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. |  |  | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
Total | [13 empty] | 348.58 | 164.3 | 47.13