## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Laying of pipeline for providing FHTC 100% coverage and also construction & installation of Sluice Valve & Valve Chamber to control the flow of water, road restoration work etc. of different Piped W/S Schemes, Block Jamalpur under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000194/2024-2025 | 2488/BWD | 01/07/2024 | 02/01/2026 | M/S NATIONAL CONSTRUCTION | 480.97 | 0 | 0 | 80
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/07/2025 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) at Ajhapur village (Habitation,near Head Work Site)under AJHAPUR PWSS at Jamalpur Dev. Block of Burdwan Sub-Division under Burdwan Division,PHE Dte. Gr.D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000442/2022-2023 | 1480/BSD | 25/08/2022 | 24/09/2022 | T.K. BANERJEE & CO. | 3.33 | 3.33 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 46/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000452/2020-2021 | 4753/BWD | 01/12/2020 | 01/03/2021 | SK ALIM | 93.16 | 45.49 | 48.83 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Providing Functional Household Tap Connection(FHTC)from existing distribution pipe line system within command area of AJHAPUR Piped W/S Scheme at Ajhapur Habitation (Near Head Works Site), Jamalpur Development Block under Burdwan Division,PHE Dte. Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000478/2022-2023 | 1602/BSD | 14/09/2022 | 14/10/2022 | DEY NIRMAN | 4.03 | 3.92 | 97.2 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of AJHAPUR & its adjoining mouzas Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000545/2022-2023 | 5124/BWD | 21/11/2022 | 21/12/2022 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 11.24 | 9.77 | 86.98 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at AJHAPUR (Jamalpur Block) P.W.S.S under Burdwan Division, PHE Dte. |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000545/2024-2025 | 276/RWS | 03/09/2024 | 13/09/2024 | DEY NIRMAN | 0.91 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AJHAPUR Piped Water Supply Scheme and its adjoining mouzas (Vill- Ajhapur, Habitation- Purba Sadipur, Musunda) at Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000578/2021-2022 | 1352/BWD | 09/03/2022 | 23/04/2022 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 41.37 | 38.97 | 94.22 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Extension of pipeline of AJHAPUR Piped Water Supply scheme of Jamalpur Block under Burdwan Sub-Division,under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000581/2022-2023 | 1978/BSD | 17/11/2022 | 02/12/2022 | DEY NIRMAN | 0.51 | 0.51 | 100 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for AJHAPUR its Adjoining Mouza W/S Scheme, Block -Jamalpur within Burdwan Sub-Division, PHE Dte. (Mouza- SALMULA) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000841/2022-2023 | 507/BSD | 21/03/2023 | 05/05/2023 | M/S MA TARA ENTERPRISE | 3.29 | 2.78 | 84.53 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Construction of Boundary wall at 4th Tubewell site with Inter Connection and providing FHTC at Mirepara, Adampur, Shalmula Village (Habitation) of AJHAPUR Water Supply Scheme under JAMALPUR Block of Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/001040/2023-2024 | 783/BWD | 27/02/2024 | 28/03/2024 | MUNSHI JAVEDUR JAMAN | 14.96 | 12.75 | 85.23 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | AE(HQs),AE(HQs), Burdwan Division, PHE Dte. | Junior Engineer, Burdwan Division | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 20/05/2025 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Construction of overhead structure for placing 2 Nos 5000 lit PVC tank including interconnection, Installation of Solar pump, FHTC, LDS & Sinking of 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe at Mohanpur village for AJHAPUR Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. | AE(HQs) |  | ORD/001251/2024-2025 | 817/BWD | 04/03/2025 | 02/06/2025 | UJJWAL MUKHERJEE | 23.02 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 422/BWD | 20/01/2022 | 20/01/2022 | Resource Division | 5.49 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08701 | Retrofitting | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. |  |  | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
Total | [13 empty] | 1187.25 | 117.52 | 9.9