## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08715 | Retrofitting | Construction of concrete path way at Head Work Site & 2nd & 3rd Tube Well site along with plinth protection of Pump House No-I & laying of 200 mm dia DI Pipe for wash out and over flow drain of existing OHR of Putsuri W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000038/2022-2023 | 2218/BWD | 28/04/2022 | 28/05/2022 | BISHWAJIT DAS | 4.07 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08715 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Putsuri Piped Water Supply Scheme at Denur (6 Nos Habitation Part) & Putsuri (11 Nos Habitation Part) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.(Agreement No. 55/2020-2021 OF SE/CC/PHE. DTE.) | AE(HQs) | J.E. 2 BURDWAN | ORD/000125/2020-2021 | 4887/BWD | 07/12/2020 | 07/03/2021 | M/S S. CHOUDHURY | 77.12 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08715 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PUTSURI Piped Water Supply Scheme at Kasa (6 Nos. Habs.), Purba Balarampur, Bhurkunda (7 Nos. Habs.), Patun (5 Nos. Habs.) & Bigha (3 Nos. Habs.) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000302/2021-2022 | 7020/BWD | 17/12/2021 | 15/02/2022 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 53.94 | 45.21 | 83.8 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08715 | Retrofitting | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 10/11/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08715 | Retrofitting | Sinking of Tube Well, Construction of Pump House, Boundary wall & interconnection work of Kasa village of PUTSURI Water Supply Scheme within Kalna Sub-Division under Burdwan division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer ,Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000721/2023-2024 | 4532/BWD | 13/10/2023 | 12/12/2023 | B.S. ENTERPRISE | 27.32 | 7.27 | 26.61 | 40
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08715 | Retrofitting | Laying of different dia.UPVC pipeline at the damaged portion from Denur to Mousa Daukadanga under Putsuri & its adjoining mouzas water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000778/2021-2022 | 6013/BWD | 05/10/2021 | 04/11/2021 | D.M. ENTERPRISE | 23.17 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08715 | Retrofitting | Construction of Pump House cum switch room (5.40m x 3.60m) with sanitary arrangement (As per drawing no-PHE/SE/CC/PH/ DWG-01/2022-2023) at Aug. of MANTESWAR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. 1 No Pump House. | Assistant Engineer |  | ORD/001013/2023-2024 | 467/BWD | 05/02/2024 | 05/04/2024 | BISHWAJIT DAS | 5.86 | 0 | 0 | 0
Total | [13 empty] | 501.08 | 52.48 | 10.47