## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. | SM/09241 | Support-WQMSP | Hire charges of 62.5 KVA Diesel Generator set for District Laboratory NABL Audit purpose including engagement one operator Technician and Diesel (8lit/hour) and all other incidental charges. |  |  | BILL/00515/2024-2025 | 690/JJM | 14/08/2024 |  | KHUSI BHAKAT | 0.08 | 0 | 0 | null
2 | PURBA BARDHAMAN |  | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. | SM/09241 | Support-WQMSP | Providing NABL related expenses for renewal audit of Burdwan District Water testing Laboratory under Burdwan Division, PHE Dte. |  | Contractual Junior Engineer,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000001/2024-2025 | 145/RWS | 18/04/2024 | 25/04/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. | SM/09241 | Support-WQMSP | Supply & Delivery of Chemicals, reagents and consumables at District Laboratory and 8 (Eight) Sub-District laboratories for NABL accreditation under Burdwan Division, P.H.E. Dte._Group : A | AE(HQs) | J.E. 2 BURDWAN | ORD/000075/2022-2023 | 290/AE/HQ | 17/05/2022 | 24/05/2022 | LAB SOLUTION | 4.23 | 4.23 | 100 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. | SM/09241 | Support-WQMSP | Sanction order for deposit of annual accreditation fee for NABL Accreditation of Burdwan District Laboratory under Burdwan Division, PHE Dte. |  |  | ORD/000506/2022-2023 | 1005/BSD | 17/06/2022 | 15/09/2022 | ALAKA GHOSH | 0.28 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. | SM/09241 | Support-WQMSP | Sanction order for deposit of Final assessment fee for NABL Accreditation of Burdwan District Laboratory under Burdwan Division, PHE Dte. |  |  | ORD/000508/2022-2023 | 877/BSD | 24/05/2022 | 22/08/2022 | ALAKA GHOSH | 0.25 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. | SM/09241 | Support-WQMSP | Supply & installation of approved quality Curtain with fixing of other allied works for NABL recognition of District Laboratory, Nababhat PHE Complex under Burdwan Divn., PHE. Dte. [Group : E] | AE(HQs) | J.E. 2 BURDWAN | ORD/000735/2021-2022 | 160/AE/HQ | 17/03/2022 | 27/03/2022 | BHARAT CONSTRUCTION | 0.79 | 0.79 | 100 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. | SM/09241 | Support-WQMSP | Procurement of Equipment's, Glassware and Chemicals required for NABL accreditation of the District Laboratory at Nababhat under Burdwan Division, PHE Dte._2nd Call. | AE(HQs) | J.E. 2 BURDWAN | ORD/000763/2021-2022 | 6769/BWD | 03/12/2021 | 23/12/2021 | LAB SOLUTION | 9.15 | 8.48 | 92.69 | 0
Total | [13 empty] | 16.07 | 14.78 | 91.98