## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Quotation for new connection charges of Augmentation of Barbelun w/s scheme under Burdwan Division, PHE Dte. T.W. No.-4 [Memo No.-5003603611/Quot/03, dt.-10/02/2023][App No.-5003603611, Ref. ID-503282585] |  |  | BILL/00291/2022-2023 | 1115/JJM | 27/02/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.4 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for Augmentation of BAROBELUN Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000013/2022-2023 | 1961/BWD | 12/04/2022 | 27/05/2022 | ACME CONSTRUCTION | 22.05 | 16.18 | 73.4 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000311/2022-2023 | 3624/BWD | 22/08/2022 | 11/09/2022 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Beautification of PWSS with Arboriculture, Recharge Pit including shaft at Head Works site and anciliary works at 1st & 4th Tubewell site of BARABELUN (Bhatar Block) P.W.S.S under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000367/2024-2025 | 238/RWS | 30/07/2024 | 09/08/2024 | GHOSH ENTERPRISE | 0.97 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Augmentation of BARABELUN Piped Water Supply Scheme with LDS, FHTC work, Rising Main, Switch Room (with water supply & sanitary arrangements), 400 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Boundary wall construction (HW, 2nd TW & 4th TW Site) with repairing of switch room cum chlorine room, Block - Bhatar, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000423/2021-2022 | 571/BWD | 27/01/2022 | 22/01/2023 | MD HASIN | 406.41 | 385.05 | 94.74 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Route Survey & Preparation of DPR for BARABELUN PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000656/2021-2022 | 105/DSD | 18/02/2022 | 05/03/2022 | RISHAN ENGINEERING CONSULTANCY | 2.72 | 2.72 | 100 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Land development and beautification with plant and Construction of connecting road from Gate to Pumphouse, OHR at 1st tubewell site of Barobelun Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000986/2023-2024 | 42/DSD | 17/01/2024 | 17/01/2025 | MUNSHI JAVEDUR JAMAN | 4.82 | 1.76 | 36.62 | 72
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Providing Functional Household Tap Connection (FHTC)from distribution system within the command area of Barobelun water supply scheme at Baneswarpur village under JJM under Bhatar Block in Purba Bardhanan District undrer Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001019/2023-2024 | 130/DSD | 07/02/2024 | 23/03/2024 | JAMALUDDIN SK | 3.02 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Providing Functional Household Tap Connection (FHTC)from distribution system within the command area of Barobelun water supply scheme at Khulla village under JJM under Bhatar Block in Purba Bardhanan District undrer Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001020/2023-2024 | 131/DSD | 07/02/2024 | 23/03/2024 | JAMALUDDIN SK | 1.81 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2021-2022 | 556/BWD | 27/01/2022 |  | Resource Division | 13.64 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 4854/BWD | 20/10/2022 |  | Resource Division | 6.16 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2021-2022 | 770/BWD | 07/02/2022 |  | Resource Division | 26.55 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000168/2021-2022 | 1328/BWD | 08/03/2022 |  | Resource Division | 39.89 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000186/2021-2022 | 1381/BWD | 09/03/2022 |  | Resource Division | 4.35 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000236/2021-2022 | 1560/BWD | 15/03/2022 |  | Resource Division | 0.37 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | New connection charges bill for Barabelun water supply scheme under Burdwan Division, PHE Dte.[Application No.-5003437581, Ref ID-503142125] |  |  | VCH/000524/2022-2023 | 596/DW/22-23 | 21/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.9 | 0 | 0 | 0
17 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of Barabelun Water Supply Scheme [ Block- Bhatar ] at 1st Tube well Site( Tube well No.-3) at under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER |  | ORD/000619/2022-2023 | 2095/CMD | 08/09/2022 | 08/10/2022 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.9 | 10.57 | 96.95 | 0
19 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | SM/09700 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of Barabelun Water Supply Scheme [ Block- Bhatar ] at 2nd Tube well Site( Tube well No.-4) at under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000621/2022-2023 | 2094/CMD | 08/09/2022 | 08/10/2022 | M/S. SWAPAN BANERJEE | 11.4 | 11.14 | 97.79 | 100
Total | [13 empty] | 3581.12 | 427.43 | 11.94