## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 50 (Fifty) Nos. Anganwadi Center having Electric Power connection within the command area of Memari - I Block under Burdwan Division, P.H.E. Dte. (Part - B). | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000019/2021-2022 | 3299/BWD | 15/06/2021 | 15/07/2021 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 23.93 | 20.97 | 87.65 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 50 (Fifty) Nos. Anganwadi Center having Electric Power connection within the command area of Memari - I Block under Burdwan Division, P.H.E. Dte. (Part - A). | Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000021/2021-2022 | 3334/BWD | 18/06/2021 | 18/07/2021 | BRINDABAN KONAR | 23.9 | 20.74 | 86.79 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 50 (Fifty) Nos. Anganwadi Center having Electric Power connection within the command area of Katwa - I Block (22 Nos.) & Katwa - II Block (28 Nos.) under Burdwan Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000025/2021-2022 | 3344/BWD | 21/06/2021 | 21/07/2021 | TAPAS KUMAR ROY | 23.88 | 13.32 | 55.8 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 14 (Fourteen) Nos. Anganwadi Center having no Electric Power connection within the command area of Burdwan - I Block (04 Nos.) & Burdwan - II Block (10 Nos.) under Burdwan Division, P.H.E. Dte._2ND CALL. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000025/2022-2023 | 2035/BWD | 19/04/2022 | 19/05/2022 | GOUTAM KUMAR MITRA | 5.73 | 4.64 | 80.93 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 36 (Thirty Six) Nos. Anganwadi Center having Electric Power connection within the command area of Monteswar Block (17 Nos.) & Mongalkote Block (19 Nos.) under Burdwan Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000127/2021-2022 | 4552/BWD | 06/09/2021 | 06/10/2021 | ASMA ENTERPRISE | 17.18 | 12.92 | 75.2 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 18 (Eighteen) Nos. Anganwadi Center having Electric Power connection within the command area of Khandaghosh Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000128/2021-2022 | 4546/BWD | 06/09/2021 | 06/10/2021 | SHUBHRA KANTI GHOSH | 8.62 | 5.42 | 62.87 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 42 (Forty Two) Nos. Anganwadi Center having Electric Power connection within the command area of Memari - II Block under Burdwan Division, P.H.E. Dte. (Part - B). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000130/2021-2022 | 4548/BWD | 06/09/2021 | 06/10/2021 | BARDHAMAN AQUA ENGINEERING | 19.71 | 11.7 | 59.38 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 24 (Twenty Four) Nos. Anganwadi Center having Electric Power connection within the command area of Raina - I Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000133/2021-2022 | 4547/BWD | 06/09/2021 | 06/10/2021 | BARDHAMAN AQUA ENGINEERING | 11.29 | 7.43 | 65.77 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 54 (Fifty Four) Nos. Anganwadi Center having Electric Power connection within the command area of Jamalpur Block under Burdwan Division, P.H.E. Dte. (Part-B). | Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000134/2021-2022 | 4544/BWD | 06/09/2021 | 06/10/2021 | KOUSIK MALLICK | 25.88 | 19.21 | 74.22 | 1
10 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 42 (Forty Two) Nos. Anganwadi Center having Electric Power connection within the command area of Memari - II Block under Burdwan Division, P.H.E. Dte. (Part - A). | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000135/2021-2022 | 4550/BWD | 06/09/2021 | 06/10/2021 | SETH ENTERPRISE | 17.71 | 5.48 | 30.93 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos. Anganwadi Center having Electric Power connection within the command area of Kalna - I Block (09 Nos.) & Kalna - II Block (11 Nos.) under Burdwan Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000136/2021-2022 | 4549/BWD | 06/09/2021 | 06/10/2021 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 8.53 | 6.02 | 70.6 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 54 (Fifty Four) Nos. Anganwadi Center having no Electric Power connection within the command area of Jamalpur Block under Burdwan Division, P.H.E. Dte. (Part-A). | Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000343/2021-2022 | 38/BWD | 05/01/2022 | 04/02/2022 | HAFIJUR RAHAMAN MIDYA | 22.1 | 15.58 | 70.48 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 55 (Fifty Five) Nos. Anganwadi Center having no Electric Power connection within the command area of Raina - II Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000357/2021-2022 | 69/BWD | 06/01/2022 | 05/02/2022 | PREMANANDA ROY BISWAS | 22.28 | 18.61 | 83.5 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 58 (Fifty Eight) Nos. Anganwadi Center having no Electric Power connection within the command area of Ausgram - II Block under Burdwan Division, P.H.E. Dte. (Part-A). | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000361/2021-2022 | 106/BWD | 06/01/2022 | 05/02/2022 | ANWESHA CONSTRUCTION | 23.05 | 21.89 | 94.98 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 69 (Sixty Nine) Nos. Anganwadi Center having no Electric Power connection within the command area of Ausgram - I Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000362/2021-2022 | 107/BWD | 06/01/2022 | 05/02/2022 | DUBE ENTERPRISE | 27.96 | 26.2 | 93.71 | 1
16 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 30 (Thirty) Nos. Anganwadi Center having no Electric Power connection within the command area of Bhatar Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000374/2021-2022 | 212/BWD | 11/01/2022 | 10/02/2022 | BAMDEB CONSTRUCTION & CO | 12.29 | 10.27 | 83.58 | 1
17 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 57 (Fifty Seven) Nos. Anganwadi Center having no Electric Power connection within the command area of Ausgram - II Block under Burdwan Division, P.H.E. Dte. (Part-B). | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000403/2021-2022 | 281/BWD | 17/01/2022 | 16/02/2022 | RELIABLE ENGINEERS CO.-OPERATIVE CONSTRUCTION SOCIETY LTD. | 23.46 | 16.25 | 69.3 | 1
18 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos. Anganwadi Center having no Electric Power connection within the command area of Galsi - II Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000404/2021-2022 | 282/BWD | 17/01/2022 | 16/02/2022 | J. K. CORPORATION | 8.11 | 7.94 | 97.83 | 1
19 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 53 (Fifty Three) Nos. Anganwadi Center having no Electric Power connection within the command area of Purbasthali - I Block (36 Nos.) & Purbasthali - II Block (17 Nos.) under Burdwan Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000447/2021-2022 | 754/BWD | 07/02/2022 | 09/03/2022 | BIPLAB GUHA | 21.61 | 18.34 | 84.85 | 1
20 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 58 Nos Anganwari Centre having Electric Power connection within the command area of Memari-I Block under Burdwan Division, PHE Dte. [Part-C] | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000536/2021-2022 | 3203/BWD | 09/06/2021 | 09/07/2021 | G.S. CONSTRUCTION & CO. | 27.75 | 26.07 | 93.95 | 1
21 | PURBA BARDHAMAN |  | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. | SM/10016 | Anganwadi | Providing necessary water supply arrangement at 51 (Fifty One) Nos. Anganwadi Center having Electric Power connection within the command area of Galsi - I Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000787/2021-2022 | 4545./BWD | 06/09/2021 | 06/10/2021 | SHUBHRA KANTI GHOSH | 24.42 | 15.45 | 63.27 | 1
Total | [13 empty] | 399.38 | 304.45 | 76.23