## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Restoration of existing concrete road and HDD Boring for laying distribution system of augmentation of Dhatrigram Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000079/2023-2024 | 2055/BWD | 04/05/2023 | 03/07/2023 | PUSPA ENTERPRISE | 38.67 | 38.67 | 100 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Augmentation of Dhatrigram Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of new 500 cum capacity OHR with 20.0 mtr. Staging height with soil investigation including construction of 5(five) nos. switch-room(5.40mx3.6m), construction of five nos. new boundary wall for new TW sites & repairing of existing OHR, switch room & boundary wall under Kalna-I Block, District:- Purba-Burdwan. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000145/2022-2023 | 3046/BWD | 08/07/2022 | 08/07/2023 | PUSPA ENTERPRISE | 697.5 | 549.48 | 78.78 | 70
3 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of DHATRIGRAM Piped Water Supply Scheme, Block - Kalna - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. |  |  | ORD/000219/2023-2024 | 2710/BWD | 08/06/2023 | 23/07/2023 | AUXILIARY TUBE WELL DRILLERS | 19.76 | 18.22 | 92.2 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Preparation of DPR for augmentation of Dhatrigram W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-C) | Assistant Engineer |  | ORD/000515/2021-2022 | 183/KSD | 21/02/2022 | 14/03/2022 | LEMNISCATE | 3.17 | 3.17 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Shifting of pipe line of DHATRIGRAM Piped Water Supply Scheme for widening of road from Nabadwip more to Dhatrigram rail gate along the Dhatrigram-Burdwan road within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000685/2023-2024 | 4281/BWD | 29/09/2023 | 28/11/2023 | IYASIN DAFADAR | 11.99 | 4.76 | 39.68 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Additional pipe laying and other allied works of distribution system for construction of New OHR Site within the command area of Aug. of DHATRIGRAM Piped Water Supply Scheme of KALNA Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000967/2023-2024 | 004/BWD | 02/01/2024 | 02/03/2024 | PUSPA ENTERPRISE | 55.13 | 8.99 | 16.31 | 33
7 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 4850/BWD | 20/10/2022 |  | Resource Division | 15.4 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000145/2021-2022 | 1219/BWD | 04/03/2022 |  | Resource Division | 22.68 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000178/2021-2022 | 1336/BWD | 08/03/2022 |  | Resource Division | 70.03 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000187/2021-2022 | 1382/BWD | 09/03/2022 |  | Resource Division | 3.88 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000230/2021-2022 | 1552/BWD | 15/03/2022 |  | Resource Division | 0.37 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 |  | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Additional Quotation for new service connection for Dhatrigram Daspara PWSS . |  |  | BILL/00310/2024-2025 | BP-2024-25-151 | 21/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.45 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | New service connection charges for Dhatrigram PWSS TW 4 |  |  | BILL/01485/2023-2024 | BP-2023-24-181 | 04/10/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.35 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | New service connection charges for Dhatrigram PWSS TW-7 |  |  | BILL/01487/2023-2024 | BP-2023-24-182 | 04/10/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.36 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Supply and Installation of Submersible Pumping Machinery for breakdown maintenance along with allied accessories for Tube Well no- 3A & Lowering of pumping machinery at T.W-3B at DHATRIGRAM and some other works at jot raghab & Deriapur Water Supply Scheme, under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000109/2023-2024 | 387/CMSD-I | 19/04/2023 | 10/05/2023 | CHOUDHURY ENTERPRISE | 0.69 | 0.69 | 100 | 0
17 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Installation of a Voltage correcting device along with allied accessories at DHATRIGRAM Water Supply Scheme, Pump house-2 under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000122/2023-2024 | 497/CMSD-I | 13/06/2023 | 04/07/2023 | SUDIKSHA CONSTRUCTION | 3.48 | 3.48 | 100 | 0
18 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | SM/10270 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 4 & 5 at Augumentation of DHATRIGRAM Water Supply Scheme [BLOCK- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001612/2023-2024 | 1543/CMD | 05/03/2024 | 04/05/2024 | M/S. SWAPAN BANERJEE | 24.62 | 14.99 | 60.89 | 90
Total | [13 empty] | 3984.53 | 642.46 | 16.12