## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Burdwan-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000689/2021-2022 | 6748/BWD | 03/12/2021 | 18/12/2021 | DEBJYOTI GOSWAMI | 4.84 | 1.04 | 21.41 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Purbasthali-I Block under Burdwan Division, PHE Dte.[Part-B][SL-25] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000705/2021-2022 | 6759/BWD | 03/12/2021 | 18/12/2021 | M/S SAYAN CHAKRABORTY | 3.79 | 2.29 | 60.5 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Raina-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000706/2021-2022 | 6760/BWD | 03/12/2021 | 18/12/2021 | POMPA CONSTRUCTION CO. | 2.97 | 0.71 | 23.74 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Purbasthali-I Block under Burdwan Division, PHE Dte.[Part-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000707/2021-2022 | 6738/BWD | 03/12/2021 | 18/12/2021 | TAPAS KUMAR ROY | 3.78 | 2.21 | 58.48 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Kalna-I Block under Burdwan Division, PHE Dte.[SL-13] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000708/2021-2022 | 6752/BWD | 03/12/2021 | 18/12/2021 | BISWAS ENTERPRISE | 4.73 | 1.85 | 39.17 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Ketugram-II Block under Burdwan Division, PHE Dte.[SL-18] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000709/2021-2022 | 6757/BWD | 03/12/2021 | 18/12/2021 | ABDUL HAI | 2.97 | 2.67 | 89.97 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Purbasthali-II Block under Burdwan Division, PHE Dte.[Part-B][SL-27] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000710/2021-2022 | 6759/.BWD | 03/12/2021 | 18/12/2021 | PARTHA PRATIM ACHARYA | 4.71 | 2.79 | 59.19 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Kalna-II Block under Burdwan Division, PHE Dte.[sl-14] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000713/2021-2022 | 6753/BWD | 03/12/2021 | 18/12/2021 | M/S UNIQUE | 3.9 | 3.81 | 97.82 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Katwa-I Block under Burdwan Division, PHE Dte.[sl-15] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000721/2021-2022 | 6754/BWD | 03/12/2021 | 18/12/2021 | CHANCHAL PAL | 2.06 | 1 | 48.52 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Jamalpur Block under Burdwan Division, PHE Dte.[sl-03] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000722/2021-2022 | 6742/BWD | 03/12/2021 | 18/12/2021 | ROY CONSTRUCTION | 4.78 | 3.51 | 73.48 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Katwa-II Block under Burdwan Division, PHE Dte.[sl-16] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000723/2021-2022 | 6755/BWD | 03/12/2021 | 18/12/2021 | OM CONSTRUCTION | 1.84 | 1.17 | 63.71 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Memari-II Block under Burdwan Division, PHE Dte.[SL-23] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000729/2021-2022 | 6737/BWD | 03/12/2021 | 18/12/2021 | M/S LOKE NIRMAN | 1.39 | 1.04 | 74.87 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Burdwan-II Block under Burdwan Division, PHE Dte. [SL NO.-10] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000753/2021-2022 | 6749/BWD | 03/12/2021 | 18/12/2021 | GOUTAM KUMAR MITRA | 2.42 | 2.04 | 84.21 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Memari-I Block under Burdwan Division, PHE Dte.[SL-21] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000755/2021-2022 | 6735/BWD | 03/12/2021 | 18/12/2021 | N.S. ENTERPRISE | 3.89 | 1.31 | 33.62 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Khandaghosh Block under Burdwan Division, PHE Dte.[SL-20] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000756/2021-2022 | 6734/BWD | 03/12/2021 | 18/12/2021 | SOUMYAVASH DAS | 3.33 | 2.47 | 74.29 | 0
16 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Jamalpur Block under Burdwan Division, PHE Dte.[SL-04] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000758/2021-2022 | 6743/BWD | 03/12/2021 | 18/12/2021 | ROY BISWAS CONSTRUCTION | 4.72 | 2.67 | 56.66 | 0
17 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Bhatar Block under Burdwan Division, PHE Dte.[SL-08] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000759/2021-2022 | 6747/BWD | 03/12/2021 | 18/12/2021 | DEEPAK ENTERPRISE | 4.47 | 0.59 | 13.14 | 0
18 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Memari-I Block under Burdwan Division, PHE Dte.[SL-22] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000761/2021-2022 | 6736/BWD | 03/12/2021 | 18/12/2021 | A R TRADERS | 4.01 | 1.74 | 43.37 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Monteswar Block under Burdwan Division, PHE Dte.[SL-22] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000762/2021-2022 | 6733/BWD | 03/12/2021 | 18/12/2021 | PRONAB KUMAR DEY | 4.01 | 2.29 | 57.03 | 0
20 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Ausgram-II Block under Burdwan Division, PHE Dte.[SL-06] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000771/2021-2022 | 6745/BWD | 03/12/2021 | 18/12/2021 | TARAMA AGENCY | 2.42 | 0.42 | 17.46 | 0
21 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Purbasthali-II Block under Burdwan Division, PHE Dte. [Part-A][SL-26] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000782/2021-2022 | 6758/BWD | 03/12/2021 | 18/12/2021 | MOYAZZEM CONSTRUCTION | 4.67 | 2.07 | 44.22 | 0
22 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Galsi-I Block under Burdwan Division, PHE Dte.[SL-11] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000788/2021-2022 | 6750/BWD | 03/12/2021 | 18/12/2021 | PAPRI HAZRA | 4.67 | 2.33 | 49.83 | 0
23 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Jamalpur Block under Burdwan Division, PHE Dte. [Part-A][Sl-01] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000789/2021-2022 | 6740/BWD | 03/12/2021 | 18/12/2021 | MUKHERJEE ENTERPRISE | 4.77 | 2.85 | 59.72 | 0
24 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. [Part-B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000791/2021-2022 | 674/BWD | 03/12/2021 | 18/12/2021 | KAJAL MUKHERJEE | 4.77 | 1.84 | 38.5 | 0
25 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Mongalkote Block under Burdwan Division, PHE Dte.[SL-30] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000811/2021-2022 | 6762/BWD | 03/12/2021 | 18/12/2021 | ASMA ENTERPRISE | 3.45 | 2.71 | 78.42 | 0
26 | PURBA BARDHAMAN |  | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan | SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within the scheme jurisdiction of different piped water supply schemes within Ketugram-I Block under Burdwan Division, PHE Dte. [SL-17] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000931/2021-2022 | 6756/BWD | 03/12/2021 | 18/12/2021 | DULU MIDDA | 4.71 | 4.07 | 86.42 | 100
Total | [13 empty] | 98.07 | 53.47 | 54.52