## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Quotation from WBSEDCL for new connection charges of Selimabad w/s scheme of T.W.-3 under Burdwan Division, PHE Dte. |  |  | BILL/01932/2023-2024 | 1824/JJM | 27/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.47 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Augmentation of SELIMABAD Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 350 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including construction of switch-rooms (5.40mx3.6m) & Boundary walls for new TW site under Jamalpur Block, District:- Purba-Burdwan. [Treated as "New Scheme in place of Augmentation" vide Corrigendum Notice No. 1545/CC, dated 02.08.2022.] | AE(HQs) | J.E. 3 BURDWAN,Junior Engineer, Burdwan Division | ORD/000234/2022-2023 | 3386/BWD | 04/08/2022 | 04/08/2023 | S. DUTTA | 435.08 | 243.52 | 55.97 | 70
3 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/000439/2024-2025 | 304/AE/HQ | 31/05/2024 | 30/07/2024 | SK. ASRAFUDDIN | 0.8 | 0.8 | 99.71 | 0
4 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | AE(HQs) | Contractual Junior Engineer | ORD/000506/2024-2025 | 545/AE/HQ | 01/08/2024 | 30/09/2024 | SK. ASRAFUDDIN | 0.8 | 0.8 | 99.86 | 0
5 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001206/2023-2024 | 44/AE/HQ | 29/01/2024 | 29/03/2024 | SK. ASRAFUDDIN | 0.8 | 0.8 | 99.9 | 50
6 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001232/2023-2024 | 226/AE/HQ | 27/03/2024 | 26/05/2024 | SK. ASRAFUDDIN | 0.8 | 0.8 | 99.66 | 0
7 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 5524/BWD | 23/12/2022 |  | Resource Division | 12.41 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 5.49 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Additional Quotation for new service connection at Selimabad PWSS PH-3. |  |  | BILL/00460/2024-2025 | BP-2024-25-248 | 01/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.95 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | New service connection charges for Selimabad W/S Scheme TW-1 |  |  | BILL/00607/2023-2024 | BP-2023-24-16 | 22/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.37 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | New service connection charges for Selimabad PWSS TW-2 |  |  | BILL/01523/2023-2024 | BP-2023-24-191 | 09/10/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.82 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | NEW SERVICE CONNECTION FOR SELIMABAD PWSS. |  |  | BILL/02698/2023-2024 | BP-2023-24-565 | 23/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.66 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Selimabad Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000611/2022-2023 | 3117/CMD | 23/11/2022 | 23/12/2022 | M/S. DAS ELECTRIC CO. | 11.08 | 10.67 | 96.28 | 80
14 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Selimabad Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000612/2022-2023 | 3118/CMD | 23/11/2022 | 23/12/2022 | SUBRATA BHADRA | 11.07 | 5.36 | 48.41 | 95
15 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Selimabad Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman |  |  | ORD/000615/2022-2023 | 3119/CMD | 23/11/2022 | 23/12/2022 | MITRA ENTERPRISE | 10.73 | 0 | 0 | 0
16 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Providing pea size Gravels and Bentonite Powder sodium based at site with other works for construction of tube well at Selimabad PWSS( TW-III),Jamalpur Block under Purba Bardhaman ,Central Drilling Division, P.H.E Dte | Driller In Charge | Junior Engineer | ORD/000064/2023-2024 | 269/CMSD-I(D) | 04/12/2023 | 19/12/2023 | C.M. ENTERPRISE | 1.88 | 0.39 | 20.67 | 100
17 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Providing Tube well materials Conforming to IS: 12818:2010 with other Works at site for construction of Tube Well at Selimabad PWSS (TW-III),Jamalpur Block under Purba Bardhaman , Central Drilling Division, P.H.E Dte. | Driller In Charge | Junior Engineer | ORD/000065/2023-2024 | 271/CMSD-I(D) | 04/12/2023 | 19/12/2023 | C.M. ENTERPRISE | 3.28 | 1.2 | 36.48 | 100
18 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Providing drilling crews for construction of TW (250mm x 150mm) by Departmental Rig machine for Selimabad PWSS (TW-III), Jamalpur block under Purba Midnapur, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000146/2023-2024 | 270/CMSD-I(D) | 04/12/2023 | 19/12/2023 | C.M. ENTERPRISE | 1.73 | 0.78 | 44.96 | 100
19 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR SELIMABAD PWSS (TW-I), JAMALPUR BLOCK UNDER PURBA BARDAMAN, CDD, PHE DTE. |  |  | ORD/000285/2022-2023 | 312/CMSD-I | 22/07/2022 | 06/08/2022 | UTTAM KUMAR CHATTERJEE | 1.74 | 1.38 | 79.26 | 1
20 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | PROVIDING TUBE WELLMATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT SELIMABAD PWSS (TW-I), JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000286/2022-2023 | 313/CMSD-I | 22/07/2022 | 06/08/2022 | UTTAM KUMAR CHATTERJEE | 3.29 | 3.16 | 96.09 | 1
21 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT SELIMABAD PWSS (TW-I), JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. |  |  | ORD/000291/2022-2023 | 315/CMSD-I | 12/07/2022 | 27/07/2022 | UTTAM KUMAR CHATTERJEE | 1.88 | 1.19 | 63.31 | 1
22 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm) by utilising Departmental machineries for Selimabad PWSS(TW-I), Jamalpur block under Purba Bardhaman District, CDD PHE Dte. |  |  | ORD/000450/2022-2023 | 322/CMSD-I(D) | 12/07/2022 | 27/07/2022 | M/S SREEJIT ENTERPRISE | 1.73 | 1.55 | 89.93 | 100
23 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Providing pea size Gravels and Bentonite Powder sodium based at site with other works for construction of Tube well at Selimabad PWSS(TW-II), Jamalpur block under Purba Bardhaman District, CDD PHE Dte. |  |  | ORD/000451/2022-2023 | 324/CMSD-I(D) | 12/07/2022 | 27/07/2022 | M/S SREEJIT ENTERPRISE | 1.88 | 1.16 | 61.53 | 100
24 | PURBA BARDHAMAN | Jamalpur | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN | SM/11492 | New | Providing Tube well materials conforming to IS: 12818:2010 with other works at site for construction of Tube well at Selimabad PWSS(TW-II), Jamalpur block under Purba Bardhaman District, CDD PHE Dte. |  |  | ORD/000452/2022-2023 | 321/CMSD-I(D) | 12/07/2022 | 27/07/2022 | M/S SREEJIT ENTERPRISE | 3.28 | 3.24 | 98.69 | 100
Total | [13 empty] | 535.03 | 276.78 | 51.73