## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | BAGPUR PIPED WATER SUPPLY SCHEME | SM/13323 | New | Different types of works in connection with implementation of MIRGAHAR Piped Water Supply Scheme (SM/18365) & BAGPUR PWSS (SM/13323) under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000186/2024-2025 | 2400/BWD | 26/06/2024 | 24/10/2024 | M/S S. CHOUDHURY | 301.24 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | BAGPUR PIPED WATER SUPPLY SCHEME | SM/13323 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MANGANPUR & BAGPUR Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000391/2023-2024 | 3200/BWD | 24/07/2023 | 23/07/2024 | M/S GHOSH & CO. | 711.81 | 15.06 | 2.12 | 10
3 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | BAGPUR PIPED WATER SUPPLY SCHEME | SM/13323 | New | Material Requisition To Resource Division |  |  | RTOR000216/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 11.24 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | BAGPUR PIPED WATER SUPPLY SCHEME | SM/13323 | New | Material Requisition To Resource Division |  |  | RTOR000474/2023-2024 | 3998/BWD | 08/09/2023 |  | Resource Division | 0.83 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | BAGPUR PIPED WATER SUPPLY SCHEME | SM/13323 | New | Material Requisition To Resource Division |  |  | RTOR000796/2023-2024 | 313/BWD | 24/01/2024 |  | Resource Division | 17.19 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | BAGPUR PIPED WATER SUPPLY SCHEME | SM/13323 | New | Quotation for new service connection at Bogpur PWSS PH-1 |  |  | BILL/00389/2024-2025 | BP-2024-25-202 | 18/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.2 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | BAGPUR PIPED WATER SUPPLY SCHEME | SM/13323 | New | New service connection for BAGPUR PWSS TW-2. |  |  | BILL/02398/2023-2024 | BP-2023-24-499 | 06/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.09 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | BAGPUR PIPED WATER SUPPLY SCHEME | SM/13323 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 31/10/2024 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | BAGPUR PIPED WATER SUPPLY SCHEME | SM/13323 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at BAGPUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001273/2023-2024 | 16/CMD | 03/01/2024 | 02/02/2024 | BARMAN ROY TRADERS | 21.77 | 0 | 0 | 0
Total | [13 empty] | 1121.98 | 15.06 | 1.34