## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina - II | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME | SM/13329 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to UCHALAN, CHAK CHANDAN, SERPUR & KATNABIL Piped Water Supply Scheme under Raina II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000367/2023-2024 | 3076/BWD | 18/07/2023 | 17/07/2024 | SK ALIM | 1307.56 | 0 | 0 | 40
2 | PURBA BARDHAMAN | Raina - II | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME | SM/13329 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-08-2024 to 31-10-2024) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000557/2024-2025 | 1500/BSD | 30/07/2024 | 04/10/2024 | PARVIN BEGAM | 0.85 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina - II | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME | SM/13329 | New | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) |  |  | ORD/000985/2023-2024 | 2561/BSD | 30/10/2023 | 04/01/2024 | MD HASIN | 0.85 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina - II | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME | SM/13329 | New | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 2.75 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina - II | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME | SM/13329 | New | Material Requisition To Resource Division |  |  | RTOR000331/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 11.85 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina - II | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME | SM/13329 | New | Material Requisition To Resource Division |  |  | RTOR000478/2023-2024 | 4002/BWD | 08/09/2023 |  | Resource Division | 11.88 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina - II | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME | SM/13329 | New | Material Requisition To Resource Division |  |  | RTOR000697/2023-2024 | 5067/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina - II | Central Mechanical | UCHALAN PIPED WATER SUPPLY SCHEME | SM/13329 | New | New Service connection for Uchalan W/S Scheme PH No.-1 |  |  | BILL/01794/2023-2024 | BP-2023-24-299 | 30/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.13 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Raina - II | Central Mechanical | UCHALAN PIPED WATER SUPPLY SCHEME | SM/13329 | New | New electric connection for Uchalan PWSS, PH-2. |  |  | BILL/01882/2023-2024 | BP-2023-24-341 | 11/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.5 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Raina - II | Central Mechanical | UCHALAN PIPED WATER SUPPLY SCHEME | SM/13329 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Uchalan Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000910/2023-2024 | 4174/CMD | 29/08/2023 | 28/09/2023 | M/S, S.DAS AND ENTERPRISE. | 29.71 | 6.18 | 20.82 | 0
Total | [13 empty] | 1393.52 | 6.18 | 0.44