## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina - II | Burdwan Division | Serpur Piped Water Supply Scheme | SM/13384 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to UCHALAN, CHAK CHANDAN, SERPUR & KATNABIL Piped Water Supply Scheme under Raina II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000367/2023-2024 | 3076/BWD | 18/07/2023 | 17/07/2024 | SK ALIM | 1307.56 | 0 | 0 | 40
2 | PURBA BARDHAMAN | Raina - II | Burdwan Division | Serpur Piped Water Supply Scheme | SM/13384 | New | Material Requisition To Resource Division |  |  | RTOR000301/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 7.9 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina - II | Burdwan Division | Serpur Piped Water Supply Scheme | SM/13384 | New | Material Requisition To Resource Division |  |  | RTOR000483/2023-2024 | 4007/BWD | 08/09/2023 |  | Resource Division | 2.05 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina - II | Burdwan Division | Serpur Piped Water Supply Scheme | SM/13384 | New | Material Requisition To Resource Division |  |  | RTOR000692/2023-2024 | 5073/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina - II | Central Mechanical | Serpur Piped Water Supply Scheme | SM/13384 | New | NEW SERVICE CONNECTION FOR SERPUR PWSS PH-2 |  |  | BILL/00107/2024-2025 | BP-2024-25-43 | 26/04/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.23 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina - II | Central Mechanical | Serpur Piped Water Supply Scheme | SM/13384 | New | New Service connection for Serpur W/S Scheme PH No.-I |  |  | BILL/01797/2023-2024 | BP-2023-24-301 | 30/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina - II | Central Mechanical | Serpur Piped Water Supply Scheme | SM/13384 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Serpur Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000651/2023-2024 | 3994/CMD | 29/08/2023 | 28/09/2023 | S.P. CONSTRUCTION | 28.92 | 11.52 | 39.83 | 0
Total | [13 empty] | 1374.47 | 11.52 | 0.84