## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari - II | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME | SM/13423 | New | BARA PALASHAN Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000111/2023-2024 | 2300/BWD | 19/05/2023 | 18/05/2024 | MLG CONSTRUCTION | 358.59 | 79.51 | 22.17 | 52
2 | PURBA BARDHAMAN | Memari - II | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME | SM/13423 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-06-2024 to 31-08-2024" |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000228/2024-2025 | 918/BSD | 28/05/2024 | 28/08/2024 | SK. ASFIA | 1.2 | 0 | 0 | 60
3 | PURBA BARDHAMAN | Memari - II | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME | SM/13423 | New | Material Requisition To Resource Division |  |  | RTOR000234/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 23.4 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari - II | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME | SM/13423 | New | Material Requisition To Resource Division |  |  | RTOR000501/2023-2024 | 4025/BWD | 08/09/2023 |  | Resource Division | 6.08 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari - II | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME | SM/13423 | New | Material Requisition To Resource Division |  |  | RTOR000653/2023-2024 | 5099/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari - II | Central Mechanical | BARAPALASHAN PIPED WATER SUPPLY SCHEME | SM/13423 | New | New service connection at Barapalasan PWSS TW -2 |  |  | BILL/02331/2023-2024 | BP-2023-24-448 | 29/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.18 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari - II | Central Mechanical | BARAPALASHAN PIPED WATER SUPPLY SCHEME | SM/13423 | New | New service connection at Barapalasan PWSS TW -1. |  |  | BILL/02332/2023-2024 | BP-2023-24-447 | 29/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari - II | Central Mechanical | BARAPALASHAN PIPED WATER SUPPLY SCHEME | SM/13423 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 31/10/2024 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari - II | Central Mechanical | BARAPALASHAN PIPED WATER SUPPLY SCHEME | SM/13423 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Barapalashan Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000711/2023-2024 | 4022/CMD | 29/08/2023 | 28/09/2023 | MITRA ENTERPRISE | 29.26 | 5.78 | 19.74 | 0
Total | [13 empty] | 485.05 | 85.28 | 17.58