## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari - II | Burdwan Division | NOAHATI PIPED WATER SUPPLY SCHEME | SM/13452 | New | Repairing damaged Pipeline & concrete road by Cement concrete (mix 1:1.5:3) and drainage system, Sluice valve chamber for FHTC work for SATGACHIA ZONE-I, SATGACHIA ZONE-II, SRIDHARPUR, PARHATI, KUCHUT, NOAHATI, MONDALGRAM PWSS and its adjoining mouzas within MEMARI-II BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000283/2024-2025 | 2715/BWD | 11/07/2024 | 09/10/2024 | A.R. TRADERS | 74.28 | 0 | 0 | 30
2 | PURBA BARDHAMAN | Memari - II | Burdwan Division | NOAHATI PIPED WATER SUPPLY SCHEME | SM/13452 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KUCHUT & NOAHATI Piped Water Supply Scheme under Memari - II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000750/2022-2023 | 1172/BWD | 14/03/2023 | 13/03/2024 | NATIONAL CONSTRUCTION | 831.75 | 0 | 0 | 30
3 | PURBA BARDHAMAN | Memari - II | Burdwan Division | NOAHATI PIPED WATER SUPPLY SCHEME | SM/13452 | New | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 1247/BWD | 17/03/2023 |  | Resource Division | 11.94 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari - II | Burdwan Division | NOAHATI PIPED WATER SUPPLY SCHEME | SM/13452 | New | Material Requisition To Resource Division |  |  | RTOR000465/2023-2024 | 3989/BWD | 08/09/2023 |  | Resource Division | 2.9 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari - II | Burdwan Division | NOAHATI PIPED WATER SUPPLY SCHEME | SM/13452 | New | Material Requisition To Resource Division |  |  | RTOR000683/2023-2024 | 5056/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari - II | Central Mechanical | NOAHATI PIPED WATER SUPPLY SCHEME | SM/13452 | New | New service connection charges for Noahati PWSS TW-1 |  |  | BILL/00770/2023-2024 | BP-2023-24-74 | 21/07/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.87 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari - II | Central Mechanical | NOAHATI PIPED WATER SUPPLY SCHEME | SM/13452 | New | New service connection charges for Noahati PWSS TW-2 |  |  | BILL/00771/2023-2024 | BP-2023-24-75 | 21/07/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.17 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari - II | Central Mechanical | NOAHATI PIPED WATER SUPPLY SCHEME | SM/13452 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 31/10/2024 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari - II | Central Mechanical | NOAHATI PIPED WATER SUPPLY SCHEME | SM/13452 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Noahati Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000138/2023-2024 | 2819/CMD | 04/07/2023 | 03/08/2023 | M/S. S.R. ENTERPRISE | 29.4 | 23.6 | 80.28 | 100
Total | [13 empty] | 1015.75 | 23.6 | 2.32