## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | AMRA PIPED WATER SUPPLY SCHEME | SM/13454 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000008/2023-2024 | 1726/BWD | 13/04/2023 | 12/04/2024 | S.P. CONSTRUCTION | 1710.27 | 198.05 | 11.58 | 45
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | AMRA PIPED WATER SUPPLY SCHEME | SM/13454 | New | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 15.41 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | AMRA PIPED WATER SUPPLY SCHEME | SM/13454 | New | Material Requisition To Resource Division |  |  | RTOR000702/2023-2024 | 5049/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | AMRA PIPED WATER SUPPLY SCHEME | SM/13454 | New | New service connection charges for Amra PWSS TW-1 |  |  | BILL/01474/2023-2024 | BP-2023-24-172 | 29/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.84 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | AMRA PIPED WATER SUPPLY SCHEME | SM/13454 | New | New service connection charges for Amra PWSS TW-2 |  |  | BILL/01475/2023-2024 | BP-2023-24-173 | 29/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.42 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | AMRA PIPED WATER SUPPLY SCHEME | SM/13454 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 31/10/2024 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | AMRA PIPED WATER SUPPLY SCHEME | SM/13454 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amra Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000678/2023-2024 | 4010/CMD | 29/08/2023 | 28/09/2023 | M/S. SWAPAN BANERJEE | 28.98 | 1.17 | 4.03 | 0
Total | [13 empty] | 1831.18 | 199.21 | 10.88