## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari - I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/000441/2024-2025 | 307/AE/HQ | 31/05/2024 | 30/07/2024 | MD HASIN | 0.8 | 0.76 | 94.6 | 0
2 | PURBA BARDHAMAN | Memari - I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | AE(HQs) | Contractual Junior Engineer | ORD/000508/2024-2025 | 548/AE/HQ | 01/08/2024 | 30/09/2024 | MD HASIN | 0.8 | 0.36 | 45.17 | 0
3 | PURBA BARDHAMAN | Memari - I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] |  |  | ORD/000653/2023-2024 | 4076/BWD | 13/09/2023 | 03/10/2023 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 0 | 0 | 100
4 | PURBA BARDHAMAN | Memari - I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | MAGRA Piped Water Supply Scheme with Sinking of Tube-well, , Laying distribution system (LDS), Rising Main, FHTC, Construction of 250 cum capacity OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms (5.40mx3.60m) & boundary walls with gate at different TW site. Block:- Memari-I, District:- Purba-Bardhaman.[NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000672/2022-2023 | 390/BWD | 31/01/2023 | 31/01/2024 | M/S ASHA CONSTRUCTION | 425.89 | 258.63 | 60.73 | 65
5 | PURBA BARDHAMAN | Memari - I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] |  |  | ORD/000845/2023-2024 | 1759/BSD | 28/07/2023 | 02/10/2023 | MD HASIN | 0.85 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari - I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001204/2023-2024 | 42/AE/HQ | 29/01/2024 | 29/03/2024 | MD HASIN | 0.8 | 0.76 | 94.53 | 50
7 | PURBA BARDHAMAN | Memari - I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | AE(HQs) | J.E. 1 BURDWAN | ORD/001230/2023-2024 | 233/AE/HQ | 28/03/2024 | 27/05/2024 | MD HASIN | 0.8 | 0.74 | 92.73 | 0
8 | PURBA BARDHAMAN | Memari - I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 1251/BWD | 17/03/2023 |  | Resource Division | 12.34 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari - I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Material Requisition To Resource Division |  |  | RTOR000462/2023-2024 | 3986/BWD | 08/09/2023 |  | Resource Division | 8.96 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari - I | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Material Requisition To Resource Division |  |  | RTOR000676/2023-2024 | 5080/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Memari - I | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | New service connection for Magra W/S Sechem. |  |  | BILL/02184/2023-2024 | BP-2023-24-379 | 16/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.1 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Memari - I | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | New Service connection for Magra PWSS TW-2. |  |  | BILL/02338/2023-2024 | BP-2023-24-474 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Memari - I | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Memari - I | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK | SM/13491 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Magra Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000650/2023-2024 | 3993/CMD | 29/08/2023 | 28/09/2023 | ORIENTAL ENGINEERING CO. | 29.35 | 4.24 | 14.44 | 40
Total | [13 empty] | 583.1 | 265.48 | 45.53