## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | New | Different Types of work involved in connection with Augmentation of RAHATPUR (SM/16306) & LAKSHMANPUR (SM/13493) Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000176/2024-2025 | 2069/BWD | 07/06/2024 | 05/10/2024 | SAIKAT RAY | 213.73 | 0 | 0 | 2
2 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | New | LAKSHAMPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000799/2022-2023 | 1518/BWD | 28/03/2023 | 26/06/2023 | JAHAR GHOSH | 42.34 | 34.31 | 81.03 | 40
3 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | New | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 6.59 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | New | Material Requisition To Resource Division |  |  | RTOR000394/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 12.66 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | New | Material Requisition To Resource Division |  |  | RTOR000413/2023-2024 | 3867/BWD | 01/09/2023 |  | Resource Division | 0.14 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | New | New service connection charges for Lakshampur PWSS TW-1 |  |  | BILL/00752/2023-2024 | BP-2023-24-55 | 14/07/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.74 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | New | Addl. quotation for new service connection charges for Laxmanpur PWSS |  |  | BILL/01459/2023-2024 | BP-2023-24-157 | 11/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.54 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | New | New service connection for Laxmanpur PWSS PH-1 |  |  | BILL/02315/2023-2024 | BP-2023-24-454 | 30/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.01 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at LAKSHAMPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000124/2023-2024 | 2639/CMD | 14/06/2023 | 14/07/2023 | C.M. ENTERPRISE | 20.81 | 4.67 | 22.47 | 60
10 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME | SM/13493 | New | Withdrawing of pump motor set due to low discharge and installation of new pump motor set at Lakshampur PH 1 water supply scheme under CMD P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001891/2023-2024 | 363/CMSD | 28/02/2024 | 14/03/2024 | C.M. ENTERPRISE | 0.67 | 0 | 0 | 0
Total | [13 empty] | 305.24 | 38.98 | 12.77