## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina - II | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME | SM/13495 | New | CHAK BATASPUR Single Village Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000085/2023-2024 | 2115/BWD | 10/05/2023 | 08/08/2023 | ANWESHA CONSTRUCTION | 63.63 | 44.12 | 69.34 | 100
2 | PURBA BARDHAMAN | Raina - II | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME | SM/13495 | New | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and approach footway to Pump-House. Facelifting of masonary works at ANGUNA-BATASPUR (Raina-I Block) P.W.S.S under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000361/2024-2025 | 230/RWS | 25/07/2024 | 04/08/2024 | DAS ENTERPRISE | 0.97 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina - II | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME | SM/13495 | New | Beautification of PWSS with Arboriculture at Chak Bataspur and Recharge Pit including shaft & anciliary works at Head Works site and Repair and colour at 2nd Tubewell site of Kaity (Raina-II Block) P.W.S.S under Burdwan Division, PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000366/2024-2025 | 236/RWS | 30/07/2024 | 09/08/2024 | ANWESHA CONSTRUCTION | 0.97 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina - II | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME | SM/13495 | New | Material Requisition To Resource Division |  |  | RTOR000240/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 7 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina - II | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME | SM/13495 | New | Material Requisition To Resource Division |  |  | RTOR000526/2023-2024 | 4315/BWD | 29/09/2023 |  | Resource Division | 0.83 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina - II | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME | SM/13495 | New | Material Requisition To Resource Division |  |  | RTOR000659/2023-2024 | 5117/BWD | 23/11/2023 |  | Resource Division | 18.94 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina - II | Central Mechanical | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME | SM/13495 | New | New service connection charges for Chak Baraspur PWSS TW-1 |  |  | BILL/00884/2023-2024 | BP-2023-24-107 | 09/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina - II | Central Mechanical | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME | SM/13495 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAK BATASPUR Water Supply Scheme [ Block-RAINA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000165/2023-2024 | 2930/CMD | 12/07/2023 | 11/08/2023 | CONCORD ENGINEERING | 28.98 | 5.73 | 19.77 | 40
Total | [13 empty] | 124.51 | 49.85 | 40.04