## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | KARAIL PIPED WATER SUPPLY SCHEME | SM/13498 | New | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/000756/2023-2024 | 842/AE/HQ | 01/11/2023 | 16/11/2023 | M/S S. CHOUDHURY | 0.33 | 0 | 0 | 100
2 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | KARAIL PIPED WATER SUPPLY SCHEME | SM/13498 | New | KARAIL Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001010/2023-2024 | 345/BWD | 25/01/2024 | 24/05/2024 | T.K. BANERJEE & CO. | 59.45 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | KARAIL PIPED WATER SUPPLY SCHEME | SM/13498 | New | Material Requisition To Resource Division |  |  | RTOR000310/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 19.71 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | KARAIL PIPED WATER SUPPLY SCHEME | SM/13498 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 31/10/2024 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | KARAIL PIPED WATER SUPPLY SCHEME | SM/13498 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KARAIL Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000827/2023-2024 | 4104/CMD | 29/08/2023 | 28/09/2023 | PADMA ENGINEERING CO. | 20.8 | 0 | 0 | 0
Total | [13 empty] | 148.88 | 0 | 0