## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan - I | Burdwan Division | KALIGRAM PIPED WATER SUPPLY SCHEME | SM/13940 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KALIGRAM & PALITPUR Piped Water Supply Scheme under Burdwan I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000499/2023-2024 | 3532/BWD | 10/08/2023 | 09/08/2024 | SUPRITI ENTERPRISE | 704.5 | 63.8 | 9.06 | 10
2 | PURBA BARDHAMAN | Burdwan - I | Burdwan Division | KALIGRAM PIPED WATER SUPPLY SCHEME | SM/13940 | New | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 1.64 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan - I | Burdwan Division | KALIGRAM PIPED WATER SUPPLY SCHEME | SM/13940 | New | Material Requisition To Resource Division |  |  | RTOR000300/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 18.63 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan - I | Burdwan Division | KALIGRAM PIPED WATER SUPPLY SCHEME | SM/13940 | New | Material Requisition To Resource Division |  |  | RTOR000719/2023-2024 | 5272/BWD | 30/11/2023 |  | Resource Division | 21.07 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan - I | Central Mechanical | KALIGRAM PIPED WATER SUPPLY SCHEME | SM/13940 | New | New service connection charges for Kaligram PWSS TW-1 |  |  | BILL/01676/2023-2024 | BP-2023-24-225 | 10/11/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.91 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan - I | Central Mechanical | KALIGRAM PIPED WATER SUPPLY SCHEME | SM/13940 | New | Quotation for new service connection at KALIGRAM W/S Scheme PH-II. |  |  | BILL/01815/2023-2024 | BP-2023-24-305 | 30/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.57 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan - I | Central Mechanical | KALIGRAM PIPED WATER SUPPLY SCHEME | SM/13940 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan - I | Central Mechanical | KALIGRAM PIPED WATER SUPPLY SCHEME | SM/13940 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kaligram Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000655/2023-2024 | 3998/CMD | 29/08/2023 | 28/09/2023 | MITRA ENTERPRISE | 28.83 | 0 | 0 | 0
Total | [13 empty] | 838.1 | 63.8 | 7.61