## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | MOUDANGA PIPED WATER SUPPLY SCHEME | SM/14020 | New | Different types of works involve in connection with Augmentation of DIRGHAPARA (SM/07804) Water Supply Scheme, MOUDANGA (SM/ 14020) Water supply Scheme & BHANDARTIKURI (SM/14925) Water Supply Scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000357/2024-2025 | 2912/BWD | 25/07/2024 | 22/11/2024 | BANSBERIA CONSTRUCTION CO. | 293.38 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | MOUDANGA PIPED WATER SUPPLY SCHEME | SM/14020 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NAMA BHANDARITURI, SAHAPUR & MOUDANGA Piped Water Supply Scheme under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000511/2023-2024 | 3689/BWD | 23/08/2023 | 22/08/2024 | THE MAHADEV CONSTRUCTION | 734.18 | 34.24 | 4.66 | 24
3 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | MOUDANGA PIPED WATER SUPPLY SCHEME | SM/14020 | New | Material Requisition To Resource Division |  |  | RTOR000346/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 14.15 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | MOUDANGA PIPED WATER SUPPLY SCHEME | SM/14020 | New | Material Requisition To Resource Division |  |  | RTOR000511/2023-2024 | 4035/BWD | 08/09/2023 |  | Resource Division | 1.38 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | MOUDANGA PIPED WATER SUPPLY SCHEME | SM/14020 | New | Material Requisition To Resource Division |  |  | RTOR000804/2023-2024 | 305/BWD | 24/01/2024 |  | Resource Division | 17.52 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | MOUDANGA PIPED WATER SUPPLY SCHEME | SM/14020 | New | New service connection for Moudanga PH-1 PWSS. |  |  | BILL/00089/2024-2025 | BP-2024-25-28 | 19/04/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.45 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | MOUDANGA PIPED WATER SUPPLY SCHEME | SM/14020 | New | New service connection for MOUDANGA PWSS |  |  | BILL/02562/2023-2024 | BP-2023-24-546 | 19/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.78 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | MOUDANGA PIPED WATER SUPPLY SCHEME | SM/14020 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 31/10/2024 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | MOUDANGA PIPED WATER SUPPLY SCHEME | SM/14020 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MOUDANGA Water Supply Scheme [ Block- PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000829/2023-2024 | 4106/CMD | 29/08/2023 | 28/09/2023 | WEST BENGAL ENGINEERING CO. | 26.95 | 0 | 0 | 0
Total | [13 empty] | 1152.4 | 34.24 | 2.97