## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa - II | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | KALIKAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000732/2022-2023 | 1047/BWD | 09/03/2023 | 08/03/2024 | PASCON | 629.59 | 230.05 | 36.54 | 67
2 | PURBA BARDHAMAN | Katwa - II | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 1259/BWD | 17/03/2023 |  | Resource Division | 17.21 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa - II | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Material Requisition To Resource Division |  |  | RTOR000111/2022-2023 | 1645/BWD | 06/04/2023 |  | Resource Division | 14.26 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa - II | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | New service connection charges for Kalikapur PWSS TW-1 |  |  | BILL/01444/2023-2024 | BP-2023-24-155 | 07/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.07 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa - II | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | New service connection charges for Kalikapur PWSS TW-2 |  |  | BILL/01469/2023-2024 | BP-2023-24-170 | 27/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa - II | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa - II | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kalikapur Water Supply Scheme [ Block- Katwa-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000596/2023-2024 | 3953/CMD | 24/08/2023 | 23/09/2023 | M/S, S.S. ENTERPRISE. | 29.61 | 11.7 | 39.51 | 90
Total | [13 empty] | 753.36 | 241.75 | 32.09