## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna - I | Burdwan Division | NIRALGACHHI PIPED WATER SUPPLY SCHEME | SM/14436 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to TAIPARA & NIRALGACHHI Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000048/2023-2024 | 1825/BWD | 19/04/2023 | 18/04/2024 | S. GHOSH & ASSOCIATES PVT LTD. | 1064.74 | 6.63 | 0.62 | 40
2 | PURBA BARDHAMAN | Kalna - I | Burdwan Division | NIRALGACHHI PIPED WATER SUPPLY SCHEME | SM/14436 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 37.35 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna - I | Burdwan Division | NIRALGACHHI PIPED WATER SUPPLY SCHEME | SM/14436 | New | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 20.14 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna - I | Central Mechanical | NIRALGACHHI PIPED WATER SUPPLY SCHEME | SM/14436 | New | NEW SERVICE CONNECTION FOR NIRALGACHI PWSS TW-I |  |  | BILL/00106/2024-2025 | BP-2024-25-42 | 26/04/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.14 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna - I | Central Mechanical | NIRALGACHHI PIPED WATER SUPPLY SCHEME | SM/14436 | New | Quotation for new service connection at Niralgachi PWSS TW-2. |  |  | BILL/00663/2024-2025 | BP-2024-25-265 | 20/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.28 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna - I | Central Mechanical | NIRALGACHHI PIPED WATER SUPPLY SCHEME | SM/14436 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 31/10/2024 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna - I | Central Mechanical | NIRALGACHHI PIPED WATER SUPPLY SCHEME | SM/14436 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Niralgachhi Water Supply Scheme [ Block- KALNA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000759/2023-2024 | 4061/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 27.79 | 0 | 0 | 0
Total | [13 empty] | 1220.86 | 6.63 | 0.54