## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari - I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | TATARPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000375/2023-2024 | 2621/BWD | 06/06/2023 | 05/06/2024 | RANADHIR SINHA | 359.46 | 87.84 | 24.44 | 40
2 | PURBA BARDHAMAN | Memari - I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 29/05/2024 | SK.ASFIA | 2.4 | 0.4 | 16.59 | 70
3 | PURBA BARDHAMAN | Memari - I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Material Requisition To Resource Division |  |  | RTOR000330/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 10.1 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari - I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Material Requisition To Resource Division |  |  | RTOR000470/2023-2024 | 3994/BWD | 08/09/2023 |  | Resource Division | 12.51 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari - I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Material Requisition To Resource Division |  |  | RTOR000696/2023-2024 | 5059/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari - I | Central Mechanical | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | New service connection charges for Tatarpur PWSS TW-1 |  |  | BILL/01761/2023-2024 | BP-2023-24-271 | 15/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 38.7 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari - I | Central Mechanical | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | New Service connection for Tatarpur W/S Scheme PH No.-II |  |  | BILL/01792/2023-2024 | BP-2023-24-309 | 30/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.61 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari - I | Central Mechanical | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Tatarpur Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000466/2023-2024 | 3723/CMD | 08/08/2023 | 07/09/2023 | M.S. ENTERPRISE | 30.11 | 0 | 0 | 0
Total | [13 empty] | 483.33 | 88.24 | 18.26